## 🔥📉4️⃣0️⃣ (hidden)
Tasks | Feature | Bug, Improv, Feature | 3.9 Link | 4.0 Link | Priority | Status | Staff | Desciption | Comments
Connect | Tasks Container = missing entirely from 2 column view | Bug/Improvement | https://demo.backagent.net/office/tasks/ | https://design.pboffice.net/connect/ | 1 | Deployed | Ryan | Missing from page -
Connect | Tasks - Display All tasks (Not Transactional) | Bug/Improvement |  |  | 1 | Deployed | Ryan | All tasks are missing - do not display transactions in this area
Connect - Notices | Notices | Bug/Improvement |  |  | 1 | Deployed | Ryan | Functionality to add Notice not available | Added link to Add Notice page, got Add Notice page working
Connect - People | Profile - Account | Design | https://demo.backagent.net/people/profile/account/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/account/ | 1 | QA |  | Design update
Connect - People | Profile - Account | Bug/Improvement | https://demo.backagent.net/people/profile/account/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/account/ | 1 | In Progress | Ryan | Missing signature features - necessary to approve transactions
Connect - Tasks | Tasks | Bug/Improvement |  |  | 1 | Deployed | Ryan | Does not exist in 4.0 - add, edit, hierarchy
Connect - Tasks | Tasks List | Bug/Improvement |  |  | 1 | Deployed | Ryan | View all tasks
Promote: | Cannot Fullfil Print | Bug/Improvement |  |  | 1 | Deployed | Ryan | Non-functional - Cannot submit for print. Stops at review page, Throws error page (like system is down)
Start | Banners | Bug/Improvement |  | https://demo.pboffice.net/start/ | 1 | Next Up | Ryan | Bring banners back online
Transact | Tasks | Design |  |  | 1 |  |  | Display Tasks on Transact - layer into page design
Transact | Tasks | Bug/Improvement |  |  | 1 | Deployed | Ryan | Display Tasks on Transact
Transact - (Individual) | Documents | Bug/Improvement |  |  | 1 | In Progress | Ryan | Update code to save/read files from Amazon S3 | Source paths confirmed, next step to verify files
Transact - (Individual) | Documents | Design | https://demo.backagent.net/transaction/detail/documents/?8fea672f-90cf-40f0-8cd2-7b561df5b180 |  | 1 |  |  | "Documents Required Now", vs page layout and fullfillment & required documents - not enough for user to know what they should be doing Asterisk/Question mark icons are not indicative of required user behavior Search at top - What are we searching for? Hard to tell which docs are needed and which are on file (obvious in 3.9,
External Request | Client Staff Contact List Export |  |  |  | 1 | DONE | Ryan | Export of all staff from all systems for sales marketing and communications
External Request | Filter Out Expired WolfNet Feeds |  |  | https://design.pboffice.net/start/ | 1 | DONE | Ryan | Go through feed lists and identify feeds to be removed from invoice.
External Request | Export Monthly Promote Order Extract |  |  |  | 1 | DONE | Ryan | Multiple exports for accounting to process billing for Promote orders
Transact - (Individual) | Documents - Manage & Attach Document | Bug/Improvement | https://demo.backagent.net/transaction/attach/ | https://design.pboffice.net/transact/detail/checklist/?adfc806b-3514-4a9a-9b20-aab88804fe5b | 1 | Next Up | Ryan | "Save Document" should be "Create Document" and open selector After document add and upload, should take to the "drop off" page for association "Drop off page, should have better indication of completion of document requirement Document selector does not seem to be working After Document association and Save, should take user back to Transaction (e.g. "Save and Add Another" - document) Document screen status is not updating to indicate required document is satisfied Pop In Note requires styling
Transact - (Individual) | Checklist | Bug/Improvement |  | https://demo.pboffice.net/transact/detail/checklist/?adfc806b-3514-4a9a-9b20-aab88804fe5b | 1 |  | Ryan | When checking off a checklist item, should be allowed to check off, indivate not applicable, regardless of completion) Intermittant issue with Modal is frozen on top and does not dissapear after indivating ("check off task", "n/a", reset) Count on Checklist should update in real time. When checked off, and page is refreshed, same documents that were already checked off re-appear If document is statisfied, should say "On File" Cannot submit transaction if this features is not functioning - cannot get document count required to zero
Transact - (Individual) | Checklist | Design |  |  | 1 |  | Dennis | Overall asthetics
Transact - (Individual) | MLS Search Details | Bug/Improvement |  |  | 1 |  | Ryan | Requirement icon value should auto decrease as task set decreases
Navigation | Hamburger Menu - Reports | Bug/Improvement |  |  | 1 |  | Ryan | Include Associate, Office & Dynamic Reporting options
Connect | Notices - View All | Bug/Improvement | https://demo.backagent.net/office/notices/?vw=sentdept | https://design.pboffice.net/profile/notices/ | 2 |  |  | Does not work- missing ability to see sent notices and view percentage
Connect | Tasks - Transactional - appear on Transact | Bug/Improvement |  |  | 2 |  |  | Shared interface with Tasks & Transact, but as a uers I want to see my tasks in Transact
Connect - Calendar | Swap | Design | https://demo.backagent.net/office/calendar/ |  | 2 |  |  | Transaction should be red, staff events blue - bring consistent for 3.9 folks (future migrations) that are used to seeing color variations based on event type (yes - bring consistency with the colors 3.9 users are accustomed to)
Connect - Notices | Notices - Add Notice | Design |  |  | 2 |  |  | based on fields available, create modal experience
Connect - Notices | Notices - List - Identification | Design |  |  | 2 |  |  | As an admin, I want to see notices sent. As a user, I want to see notices received
Connect - People | Activity | Bug/Improvement | https://demo.backagent.net/people/profile/activity/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/activity/ | 2 |  |  | Not functioning - should be able to see all transactions within
Connect - People | Profile | Design | https://demo.backagent.net/people/profile/ | https://design.pboffice.net/profile/ | 2 |  |  | Overall Asthetics, "Show all" gets to more detail. Edit Details should bring to another screen
Connect - People | Profile | Design | https://demo.backagent.net/people/profile/contact/detail/edit/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/detail-info/ | 2 |  |  | Overall Asthetics - Edit Detail screen
Connect - People | Profile - Account | Design |  |  | 2 |  |  | Overall Asthetics - looks like 3.9
Connect - Tasks | Task Details - Add/Edit | Design |  |  | 2 |  | Dennis | Design modal based on 3.9 fields available | fixed send task sort by filters and tasks shown in cells -Dennis
Learn: | Courses | Bug/Improvement |  |  | 2 |  |  | Displays "Check back Later" pagte - should be connected
Start | Calendar View | Bug/Improvement |  | https://design.pboffice.net/start/ | 2 |  |  | Calendar View, add back in above "featured videos", slide down videos
Transact | Phase Changer Modal | Bug/Improvement |  |  | 2 |  |  | Added modal instance because of "contract termination", "full termination", "cancel..." (in 3.9, was a choose-your-own-adventure process) Designer discretion.. (during call with Seb decided to go back to cancel button below & reintroducing workflow) - Contract Term (e.g. financing fell through) system resets workflow - Full Term (e.g. Agent fired) All docs required to relinquish docs/funds and management approval
Transact | Phase Changer Modal | Design |  |  | 2 |  | Dennis | Added modal instance because of "contract termination", "full termination", "cancel..." (in 3.9, was a choose-your-own-adventure process) Designer discretion.. (during call with Seb decided to go back to cancel button below & reintroducing workflow) - Contract Term (e.g. financing fell through) system resets workflow - Full Term (e.g. Agent fired) All docs required to relinquish docs/funds and management approval
Transact | Received Files | Bug/Improvement |  |  | 2 |  |  | View works, bu there is no option to attach or view all
Transact - (Individual) | Listing Information | Design |  |  | 2 |  |  | Dates & Info Question list Read left to right?
Transact - (Individual) | MLS Search Details | Design | https://demo.backagent.net/transaction/detail/info/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | https://design.pboffice.net/transact/detail/details/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 2 |  |  | Reads left to right, "edit" should be treated different than "Not Set" - placement treatment ( click into modal experience) Details page - needs to be more consumable/better organization Required items - too much cursor travel (from left to right of screen)
Transact - (Individual) | Documents - Manage & Attach Document | Bug/Improvement |  |  | 2 |  |  | Migrate "Exempt Document" feature
Transact - (Individual) | Checklist - Due Date | Bug/Improvement |  |  | 2 |  |  | Setting action for calendar "Set Due Date"
Transact - (Individual) | Phase completion | Bug/Improvement |  |  | 2 |  |  | Can move to new phase of completion to work on - that's ok -but should not be able to complete showing if start is not already completed
Transact - (Individual) | Details | Design |  |  | 2 |  | Dennis | As questions are asked, answered quetsions, when moved to the bottom after comletion, appear to still be open and necessary. When moved to the bottom and completed they need to appear static / answered / completed
Transact - Active | Snapshot | Design |  | https://design.pboffice.net/transact/detail/snapshot/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | 2 |  | Dennis | Update Treatment throughout the page.
Transact - Summary | Actions Pulldown | Design |  |  | 2 |  |  | Followup - Unsure of functinality/behavior
Connect | Reservations - Property Time - Detail | Design |  |  | 3 |  |  | Shifts / Incremental coloration. Green --> blue depending on availability incremental availability depending on how many slots are taken throughout the day. Is blue if day is full in 3.9, Agent Photos were included - Calendar asthetics improvments requirede
Connect | Shared Docs | Bug/Improvement |  |  | 3 |  |  | Show docs on "Shared Docs" - Manager selected documentation (top 3 or 4 docs depending on column sizing)
Connect | Shared Docs Container | Design |  |  | 3 |  |  | Thumbnails displayed in Shared Docs container on Connect page
Connect | Reservations - Property Time - Detail | Design |  |  | 3 |  |  | Overall Asthetics
Connect | Reservations - Property Time - Alternates List | Design | https://demo.backagent.net/office/resources/alternates/?id=abcc2806-562f-4a6d-b244-4f039ce0161e | https://design.pboffice.net/connect/reservations/alternates/?id=abcc2806-562f-4a6d-b244-4f039ce0161e | 3 |  |  | Overall Asthetics
Connect | Reservations - Conference Room Calendar | Design | https://demo.backagent.net/office/resources/calendar/?id=1cd2d577-cc85-4bc8-9d3a-9df5748d6f45 | https://design.pboffice.net/connect/reservations/calendar/?id=1cd2d577-cc85-4bc8-9d3a-9df5748d6f45 | 3 |  |  | Overall Asthetics
Connect | People - Profile (Details) | Design |  |  | 3 |  |  | Overall Asthetics
Connect - Calendar | Filters (Show HIde) | Bug/Improvement |  | https://design.pboffice.net/connect/calendar/ | 3 |  |  | Filters not coloring or usable - filter slide in should be constant on desktop version.
Connect - Calendar | Birthdays | Bug/Improvement |  |  | 3 |  |  | When birthdays clicked on, legend dissappears
Connect - Calendar | Filter Legend | Design |  |  | 3 |  |  | Filters are highlighted in... filter (legend), uses font color in calendar, matched to highlight color in legend. Bring some consitency with legent & calendar, without making calendar noisy with highlight-colored events
Connect - Calendar | Event Detail (Update Event is OK) | Design | https://demo.backagent.net/office/calendar/detail/?fd1d7c10-4240-4759-a2f7-ea3e5250b3f6 | https://design.pboffice.net/connect/calendar/detail/?fd1d7c10-4240-4759-a2f7-ea3e5250b3f6 | 3 |  |  | Make better use of space on page. HIghlighted boxes are re-used from 3.9 General asthetics
Connect - People | Activity | Bug/Improvement |  |  | 3 |  |  | Re-introduce [Rogers Healy] Agent ratings
Connect - People | People | Bug/Improvement | https://demo.backagent.net/people/associates/ | https://design.pboffice.net/connect/people/ | 3 |  |  | "Show Staff" feature required from this area to quickly identify staff (Support uses this frequently, Offices also need this)
Connect - People | Profile - Edit Account | Design | https://demo.backagent.net/people/profile/account/activate/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/account/activate/ | 3 |  |  | Overall Asthetics - looks like 3.9
Connect - People | Profile - Settings - (Settings page AND ALL screens within) | Design |  | https://design.pboffice.net/profile/settings/ | 3 |  |  | Overall Asthetics
Connect - People | People | Design | https://demo.backagent.net/people/associates/ | https://design.pboffice.net/connect/people/ | 3 |  |  | Overall Asthetics - Looks like 3.9 Search Filters
Learn: | Vimeo Placeholder | Bug/Improvement |  |  | 3 |  |  | Video's do not appear, work to integrate vimeo channel solution - display channel content
Learn: | Video Training (Slider Display) | Bug/Improvement |  |  | 3 |  |  | Ask which to showcase in the slider (turned off for BackAgent content at the moment) 1) Backoffice 2) Office 3) Other (specified) Note - Looks like "Start" video container (except within Learn)
Navigation | Quick Links | Design |  |  | 3 |  |  | Page Styling
Navigation | Quick Links | Design |  |  | 3 |  |  | Configure Links - Styling Improvment
Navigation | "?" (right hand side) - Update System Insight | Bug/Improvement |  |  | 3 |  |  | Update "Backagent" to "BackOffice"
Promote: | Catalog | Design |  |  | 3 |  |  | Display (5?) thumbs across to fit repsonsively. Items fall below scroll and are unseen - items will then appear above & visibile
Promote: | Portfolio | Design |  |  | 3 |  |  | Text/font updates throughout, can benefit from styling
Promote: | Actions Menu --> "Order Report" | Bug/Improvement |  | https://design.pboffice.net/start/ | 3 |  |  | Managers? Template Usage & Orders? Report is not connected
Start | Date & Time Stamp | Bug/Improvement |  | https://design.pboffice.net/start/ | 3 |  |  | In addition to hamburger, add back into navigation to "Desktop"-only. On responsive dissappears, and office selector is preserved
Start | Office Selector | Design |  | https://design.pboffice.net/start/ | 3 |  |  | Make as consice as 3.9 - is too spread out
Start | Task Reminder | Design |  | https://demo.pboffice.net/start/ | 3 |  |  | Need new feature with CTA treatment indicating, manager & agent has upcoming "Tasks" - Use existing space where "Featured Headlines" exists
Transact | Received Files | Design |  |  | 3 |  | Dennis | Asthetics needed, displays faxes and all incoming files
Transact | Received Files | Bug/Improvement |  |  | 3 |  |  | Changer for category is missing for office/team (personal & not)
Transact | Send to Address Updates (email address) | Bug/Improvement |  |  | 3 |  |  | Backagent host updated to Backoffice.net
Transact | Send a fax | Design |  | https://design.pboffice.net/transact/detail/property/add/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 3 |  | Dennis | Page needs makeover (faxes essential for banks)
Transact - (Individual) | Set Property | Design |  | https://design.pboffice.net/transact/detail/property/add/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 3 |  |  | When click to choose "Set Property", loading property from MLS Listing (searching MLS)
Transact - (Individual) | Edit Property Page | Design |  | https://design.pboffice.net/transact/detail/property/add/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 3 |  |  | Search page needs improvement
Transact - (Individual) | MLS Search | Design |  | https://demo.pboffice.net/transact/detail/property/add/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 3 |  |  | Display of search page needs improvement
Transact - (Individual) | MLS Search Select | Bug/Improvement |  |  | 3 |  |  | On Selection of property, should take user back to detail page
Transact - (Individual) | Checklist - Due Date | Bug/Improvement |  |  | 3 |  |  | Action works, but due date does not appear on calendar In details number of items required does not change in realtime
Transact - (Individual) | History | Design |  | https://design.pboffice.net/transact/detail/snapshot/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | 3 |  |  | Overall asthetics
Transact - Active | Snapshot | Bug/Improvement | https://demo.backagent.net/transaction/detail/snapshot/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | https://design.pboffice.net/transact/detail/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a# | 3 |  | Dennis | Bring back "print button"
Transact - Summary | Actions Tab | Bug/Improvement | https://demo.backagent.net/transaction/detail/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | https://demo.pboffice.net/transact/detail/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a# | 3 |  |  | Quick Actions - bring (some) back to fill space. - View Snapshot - Add Note - Message Contact - Send Documents
Transact - Summary | Actions Tab | Design |  |  | 3 |  |  | Quick Actions - bring (some) back to fill space. - View Snapshot - Add Note - Message Contact - Send Documents
Navigation | Hamburger Menu - Email | Design |  |  | 3 |  |  | Overall Email asthetics
Connect | Reservations - Property Time - Detail | Design | https://demo.backagent.net/office/resources/calendar/?id=abcc2806-562f-4a6d-b244-4f039ce0161e | https://design.pboffice.net/connect/reservations/calendar/?id=abcc2806-562f-4a6d-b244-4f039ce0161e | 4 |  |  | Update color and layout Match Legend/Key to existing calendar coloration (is from 3.9) Make better use of responsiveness and existing whitespace in desktop on right hand side Update general styling (perhaps expose Alternates List in white space?)
Connect - Notices | Notices - List | Design |  |  | 4 |  |  | make better use of page layout & space
Navigation | Hamburger Menu | Bug/Improvement |  | https://design.pboffice.net/start/ | 4 |  |  | Connections - rename back to "Quick Links"
Promote: | Managing Products | Design |  |  | 4 |  |  | Styling help. Is same as 3.9 right now, but plenty of room for cont updates and improvments
Transact - (Individual) | Documents - Manage & Attach Document | Design | https://demo.backagent.net/transaction/attach/? | https://design.pboffice.net/transact/attach/? | 4 |  |  | Modal needs better interface, need a second column
Transact - Summary | People | Design |  |  | 4 |  |  | Better use of white space on page - better compression Use some sort of clickable bar for "Add Buyer", "Add Seller" - too much below scroll
Transact - Summary | People | Design | https://demo.backagent.net/transaction/detail/contacts/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | https://design.pboffice.net/transact/detail/people/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | 4 |  |  | Search Contacts modal + interaction with People screen Search on the Left side Results on the right side
Connect | Reservations Container | Design | https://demo.backagent.net/office/resources/ |  | 5 |  |  | Button for "Shifts Available" - update treatment as call-out and standardize with color scheme
Connect | Reservations Container - View All Page | Design |  | https://design.pboffice.net/connect/reservations/ | 5 |  |  | Make all thumbs same size
Connect - Calendar | Font | Design |  |  | 5 |  |  | weight - hard to see
Learn: | Display (Left to Right) sliding action | Bug/Improvement |  |  | 5 |  |  | habitually looking for red, match color categories create left right slider action display week date duration in addition to M, T, W, TH....
Learn: | Display (Left to Right) sliding action | Design |  |  | 5 |  |  | habitually looking for red, match color categories create left right slider action display week date duration in addition to M, T, W, TH....
Navigation | Quick Links | Design |  |  | 5 |  |  | Responsive positioning of Save button
Promote: | Printing | Design |  |  | 5 |  |  | 3.9 styling preserved (not horrible, works for the page, but could have a style passing
Transact | Graph - Dashboard - View Details | Bug/Improvement |  |  | 5 |  |  | Graph works for now, but "Is it good for the company?"
Transact - (Individual) | Expense | Design | https://demo.backagent.net/transaction/detail/expenses/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | https://design.pboffice.net/transact/detail/expenses/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 5 |  |  | Overall asthetics

## Design - Feedback
Tasks | Feature | Bug, Improv, Feature | 3.9 Link | 4.0 Link | Priority | Status | Staff | Description | Call Notes 03/22 | Call Notes 04/05 & Followup Meeting
Connect | Tasks Container = missing entirely from 2 column view | Bug/Improvement | https://demo.backagent.net/office/tasks/ | https://design.pboffice.net/connect/ | 1 | Deployed | Ryan | Missing from page -
Connect | Tasks - Display All tasks (Not Transactional) | Bug/Improvement |  |  | 1 | Deployed | Ryan | All tasks are missing - do not display transactions in this area
Connect - Notices | Notices | Bug/Improvement |  |  | 1 | Deployed | Ryan | Functionality to add Notice not available
Tasks | Profile - Account | Design | https://demo.backagent.net/people/profile/account/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/account/ | 1 | Changed labels to "Not Set" | Seb | Make all labels for missing info "Not Set" - remove other labels They are not links Treatment should draw the eye, but it's not all significant enough to be (e.g. bold red highlighted) - note that we have a dev task to allow for the color updates of labels et all throughout the system | #808080 - make label background color universal (gray background, white text) | done
Connect - People | Profile - Account | Bug/Improvement | https://demo.backagent.net/people/profile/account/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/account/ | 1 | In Progress | Ryan | Missing signature features - necessary to approve transactions
Connect - Tasks | Tasks | Bug/Improvement |  |  | 1 | Deployed | Ryan | Does not exist in 4.0 - add, edit, hierarchy
Connect - Tasks | Tasks List | Bug/Improvement |  |  | 1 | Deployed | Ryan | View all tasks
Promote: | Cannot Fullfil Print | Bug/Improvement |  |  | 1 | Deployed | Ryan | Non-functional - Cannot submit for print. Stops at review page, Throws error page (like system is down)
Start | Banners | Bug/Improvement |  | https://demo.pboffice.net/start/ | 1 | Next Up | Ryan | Bring banners back online
External Request | Client Staff Contact List Export | Bug/Improvement |  |  | 1 | DONE | Ryan | Export of all staff from all systems for sales marketing and communications
Transact | Tasks | Bug/Improvement |  |  | 1 | Deployed | Ryan | Display Tasks on Transact
Transact - (Individual) | Documents | Bug/Improvement |  |  | 1 | In Progress | Ryan | Update code to save/read files from Amazon S3
Transact - (Individual) | Documents | Design | https://demo.backagent.net/transaction/detail/documents/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | https://design.pboffice.net/transact/detail/documents/?adfc806b-3514-4a9a-9b20-aab88804fe5b | 1 | Done. QA needed | Dennis | Most important: Organization and (new) Icons need to indicate urgency Mouseover needs to indicate action "Attach file now" vis "Recommended File Not attached" Not easy to discern what is going on, on this page. In 3.9 is clear from color treatments | Preferred - rebuild into CSS (not images) Click-action to enable menu functionality when button is pressed Visual of doc: mouse-over of document on file | Added the verbiage "approved", "approved now" - need to bring in colors back to boxes that indicate urgency by message. 2575 Old Mill transaction has a missing icon
External Request | Filter Out Expired WolfNet Feeds | Bug/Improvement |  | https://design.pboffice.net/start/ | 1 | DONE | Ryan | Go through feed lists and identify feeds to be removed from invoice.
External Request | Export Monthly Promote Order Extract | Bug/Improvement |  |  | 1 | DONE | Ryan | Multiple exports for accounting to process billing for Promote orders
Transact - (Individual) | Documents - Manage & Attach Document | Bug/Improvement | https://demo.backagent.net/transaction/attach/ | https://design.pboffice.net/transact/detail/checklist/?adfc806b-3514-4a9a-9b20-aab88804fe5b | 1 | Next Up | Ryan | "Save Document" should be "Create Document" and open selector After document add and upload, should take to the "drop off" page for association "Drop off page, should have better indication of completion of document requirement Document selector does not seem to be working After Document association and Save, should take user back to Transaction (e.g. "Save and Add Another" - document) Document screen status is not updating to indicate required document is satisfied Pop In Note requires styling
Transact (Cancel Transaction) | Cancel Transaction (Modal) | Design |  | https://design.pboffice.net/transact/detail/update/cancel/?0ed4c56b-bf45-4097-b2cd-ede7673f1153 | 1 |  | Ryan | Removing options - except for cancellation items Preserve cancellation options and requires treatment | No selection buttons within the cancellation process walkthrough. Need some JS to make it work with CTA buttons - will look like /transact/add | done
Transact - (Individual) | Checklist | Bug/Improvement |  | https://demo.pboffice.net/transact/detail/checklist/?adfc806b-3514-4a9a-9b20-aab88804fe5b | 1 |  | Ryan | When checking off a checklist item, should be allowed to check off, indivate not applicable, regardless of completion) Intermittant issue with Modal is frozen on top and does not dissapear after indivating ("check off task", "n/a", reset) Count on Checklist should update in real time. When checked off, and page is refreshed, same documents that were already checked off re-appear If document is statisfied, should say "On File" Cannot submit transaction if this features is not functioning - cannot get document count required to zero
Transact - (Individual) | Checklist | Design |  |  | 1 |  | Dennis | Additional treatment for necessary checklist items remaining (e.g. <strong>) When phases are clicked on through the progression changer, anchoring links for each phase bring customer to that area of the larger checklist | Difference between done and non-applicable Bold for "required" items Perhaps existing treatment for "non-required" items | done
Transact - (Individual) | Documents (Choose from Inbox (now Received Files) | Design | https://demo.backagent.net/transaction/attach/?a=fax | https://design.pboffice.net/transact/attach/?a=fax | 1 |  | Dennis | (Documents tab --> Attach file), should take to inbox - unsure what secondary page is Layout for this page needs overhaul - Align document preview with Document Title and Page(s) section |  | Done
Transact - (Individual) | MLS Search Details | Bug/Improvement |  |  | 1 |  | Ryan | Requirement icon value should auto decrease as task set decreases
Transact | Search | Design | https://demo.backagent.net/transaction/active/ | https://design.pboffice.net/transact/search/ | 1 | Done | Dennis | - Icon to view "snapshot" = dated - Text above the progression circles (Authorized COA, Submitted COA, Active, etc) - we want to see progression through transaction on page (especially for admins), need a better presentation for progression and treatment for the various stages | done
Navigation | Hamburger Menu - Reports | Bug/Improvement |  |  | 1 |  | Ryan | Include Associate, Office & Dynamic Reporting options
Connect | Notices - View All | Bug/Improvement | https://demo.backagent.net/office/notices/?vw=sentdept | https://design.pboffice.net/profile/notices/ | 2 |  | Ryan? | Does not work- missing ability to see sent notices and view percentage
Connect | Tasks - Transactional - appear on Transact | Bug/Improvement |  |  | 2 |  | Ryan? | Shared interface with Tasks & Transact, but as a uers I want to see my tasks in Transact
Connect - Notices | Notices - List - Identification | Design |  |  | 2 |  | Ryan? | Links are broken - should link up with top, individual within ...connect/notices | Multiple catagories of notices - account for "i have read this notice" dependance for some Take up less space - make more compact Confirmation: (do not require typing in text), button is sufficient Refactor - tab to view "sent notices" Should work like 3.9 (contractor | done
Reports | (click icon top right, select reports) | Design |  | Staging.pboffice.net | 1 | ????? - where is this page | Seb | Page needs styling | /reports - make it look actionable for each different report | done
Connect - People | Activity | Bug/Improvement | https://demo.backagent.net/people/profile/activity/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/activity/ | 2 |  | Ryan? | Not functioning - should be able to see all transactions within
Connect - Notices | Notices - Send a Notice | Design |  |  | 4 | Done | Seb | swap columns content (left & right) - add recipients on left, content on right |  | done
Connect - People | Profile | Design | https://demo.backagent.net/people/profile/contact/detail/edit/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/detail-info/ | 2 | Ugh,think i went through all the rabbit holes on this profiles section. If u find any pages unstyled, can u attach the URL. DONE | Seb | Overall Aesthetics - LARGER TASK - We can create a JIRA for every single item or just handle it in a single line item for each For each of the Profile, Account, Settings, Activity, there are "Actions" items for each that need updates Note - we are have a JIRA - https://propertybase.atlassian.net/browse/PBBO-3193 to create a dynamic color pallete selector for | padding between tags on list page (only) | done
Connect - People | Profile - Account | Design |  |  | 2 | DONE - Both models | Seb | Overall Aesthetics - looks like 3.9 (edit account - looks ok) |  | done
Learn: | Courses | Bug/Improvement |  |  | 2 |  | Ryan? | Displays "Check back Later" pagte - should be connected
Start | Calendar View | Bug/Improvement |  | https://design.pboffice.net/start/ | 2 |  | Ryan? | Calendar View, add back in above "featured videos", slide down videos
Transact | Phase Changer Modal | Bug/Improvement |  |  | 2 |  |  | Added modal instance because of "contract termination", "full termination", "cancel..." (in 3.9, was a choose-your-own-adventure process) Designer discretion.. (during call with Seb decided to go back to cancel button below & reintroducing workflow) - Contract Term (e.g. financing fell through) system resets workflow - Full Term (e.g. Agent fired) All docs required to relinquish docs/funds and management approval
Transact | Phase Changer Modal | Design |  |  | 1 | Done? | Dennis | We want to remove the modal completely and prompt for phase changes on page No modal popup Need treatment to layer in similar options on Transact Details page. | done
Transact | Received Files | Bug/Improvement |  |  | 2 |  |  | View works, bu there is no option to attach or view all
Transact - (Individual) | Details - Listing Information | Design |  | https://design.pboffice.net/transact/detail/details/?adfc806b-3514-4a9a-9b20-aab88804fe5b | 1 |  | Dennis | Details page - needs to be more consumable/better organization Required items - too much cursor travel (from left to right of screen) Links do not work "Edit" should exist "Not Set" should be clickable link Need treatments that indicate the user has to-do's remaining After items are satisfied they disappear Should in real time update count for remaining requirement count on icons at top | Make status informational and clickable - (one in the same) | Done
Transact - (Individual) | Documents - Manage & Attach Document | Bug/Improvement |  |  | 2 |  |  | Migrate "Exempt Document" feature
Transact - (Individual) | Checklist - Due Date | Bug/Improvement |  |  | 2 |  |  | Setting action for calendar "Set Due Date"
Transact - (Individual) | Phase completion | Bug/Improvement |  |  | 2 |  |  | Can move to new phase of completion to work on - that's ok -but should not be able to complete showing if start is not already completed
Transact - (Individual) | Details - Quick Actions - Edit Property (Modal) | Design |  |  | 1 |  | Ryan | When Actions, "Edit/Set" Property, is clicked from pull down, Treatment is still 3.9 - click Search MLS or Add Now | condense bottom, bring back calendar | done
Transact - (Individual) | Details - Quick Actions - Edit Property (Modal) | Design |  |  | 1 | Done | Dennis | When Actions, "Edit/Set" Property, is clicked from pull down, Click Search MLS, Search screen needs updating Remove Search by "Street Address" Remove Search by "MLS Number" Use descriptor text on search to indicate street address and MLS numbers are searchable Ensure MLS search works | done
Transact - (Individual) | Details - Quick Actions - Edit Property (Modal) | Design |  | https://design.pboffice.net/transact/detail/property/add/?7d2be7d9-4f04-478b-8f5a-ae941d4978a0 | 1 | DONE | Dennis | Post Property Search display - Layout - needs styling | done
Transact - (Individual) | Details - Quick Actions - Edit Property (Modal) | Design |  | https://design.pboffice.net/transact/detail/property/?7d2be7d9-4f04-478b-8f5a-ae941d4978a0 | 1 | Done | Dennis | Property Select - Results Page - needs styling (should really take user back to property details tab - if design can help with that functionality) | done
Connect | Reservations - Property Time - Detail | Design |  |  | 2 | ??? | ??? | Shifts / Incremental coloration. Green --> blue depending on availability incremental availability depending on how many slots are taken throughout the day. Is blue if day is full in 3.9, Agent Photos were included - Calendar aesthetics improvements required | Weekly calendar should be main focus calendar should be made into a 'weekly' + mini calendar. Ryan to add in weekly | done
Connect | Shared Docs | Bug/Improvement |  |  | 3 |  | Ryan? | Show docs on "Shared Docs" - Manager selected documentation (top 3 or 4 docs depending on column sizing)
Connect | Shared Docs Container | Design |  |  | 3 | Done | Seb | Thumbnails displayed in Shared Docs container on Connect page |  | done
Connect | Calendar Reservation - Create | Design |  | https://design.pboffice.net/connect/calendar/update/ | 2 | Done | Seb | Overall Aesthetics | Show mini calendar | done
Connect | Reservations - Property Time - Detail | Design |  | https://design.pboffice.net/connect/calendar/detail/?b7e650f9-ce7e-4162-b115-bb85df86c732 | 3 | Done | Seb | Overall Aesthetics | Must currently go to "control panel" to update calendar event | done
Connect | Reservations - Property Time - Alternates List | Design | https://demo.backagent.net/office/resources/alternates/?id=abcc2806-562f-4a6d-b244-4f039ce0161e | https://design.pboffice.net/connect/reservations/alternates/?id=abcc2806-562f-4a6d-b244-4f039ce0161e | 3 | Done | Seb | Overall Aesthetics |  | done
Connect | Reservations - Conference Room Calendar | Design | https://demo.backagent.net/office/resources/calendar/?id=1cd2d577-cc85-4bc8-9d3a-9df5748d6f45 | https://design.pboffice.net/connect/reservations/calendar/?id=1cd2d577-cc85-4bc8-9d3a-9df5748d6f45 | 3 | Done | Seb | Overall Aesthetics |  | done
Connect | People - Profile (Details) | Design |  |  | 3 | List, details and modals DONE | Seb | Overall Aesthetics |  | done
Connect - Calendar | Filters (Show HIde) | Bug/Improvement |  | https://design.pboffice.net/connect/calendar/ | 3 | DONE | Seb | Filters not coloring or usable - filter slide in should be constant on desktop version.
Connect - Calendar | Birthdays | Bug/Improvement |  |  | 3 |  | Ryan? | When birthdays clicked on, legend dissappears
Connect - Calendar | Filter Legend | Design |  |  | 3 | DONE | Seb | Filters are highlighted in... filter (legend), uses font color in calendar, matched to highlight color in legend. Bring some consistency with legend & calendar, without making calendar noisy with highlight-colored events | test to see if brings in class selection | done
Connect - Calendar | Event Detail (Update Event is OK) | Design | https://demo.backagent.net/office/calendar/detail/?fd1d7c10-4240-4759-a2f7-ea3e5250b3f6 | https://design.pboffice.net/connect/calendar/detail/?fd1d7c10-4240-4759-a2f7-ea3e5250b3f6 | 3 | DONE | Seb | Make better use of space on page. HIghlighted boxes are reused from 3.9 General aesthetics |  | done
Connect - People | Activity | Bug/Improvement |  |  | 3 |  | Ryan? | Re-introduce [Rogers Healy] Agent ratings
Connect - People | People | Bug/Improvement | https://demo.backagent.net/people/associates/ | https://design.pboffice.net/connect/people/ | 3 |  | Ryan? | "Show Staff" feature required from this area to quickly identify staff (Support uses this frequently, Offices also need this)
Connect - People | Profile - Edit Account | Design | https://demo.backagent.net/people/profile/account/activate/?1deea0ae-3044-4f5e-87ff-9de056be3faa | https://design.pboffice.net/profile/account/activate/ | 3 | DONE | Seb | Overall Aesthetics - looks like 3.9 |  | done
Connect - People | Profile - Settings - (Settings page AND ALL screens within) | Design |  | https://design.pboffice.net/profile/settings/ | 3 | DONE | Seb | Overall Aesthetics |  | done
Connect - People | People | Design | https://demo.backagent.net/people/associates/ | https://design.pboffice.net/connect/people/ | 3 | DONE | Seb | Overall Aesthetics - Looks like 3.9 Search Filters |  | done
Learn: | Vimeo Placeholder | Bug/Improvement |  |  | 3 |  | Ryan? | Video's do not appear, work to integrate vimeo channel solution - display channel content
Learn: | Video Training (Slider Display) | Bug/Improvement |  |  | 3 |  | Ryan? | Ask which to showcase in the slider (turned off for BackAgent content at the moment) 1) Backoffice 2) Office 3) Other (specified) Note - Looks like "Start" video container (except within Learn)
Navigation | Quick Links | Design |  |  | 3 | DONE | Seb | Page Styling |  | done
Navigation | Quick Links | Design |  |  | 3 | DONE | Seb | Configure Links - Styling Improvement |  | done
Navigation | "?" (right hand side) - Update System Insight | Bug/Improvement |  |  | 3 | DONE | Seb | Update "Backagent" to "BackOffice"
Promote: | Portfolio | Design |  | https://design.pboffice.net/promote/portfolio/ | 2 | DONE | Seb | Display (5?) thumbs across to fit repsonsively. Items fall below scroll and are unseen - items will then appear above & visibile |  | discussed new treatment to get display above the scroll
Promote: | Catalog | Design |  |  | 3 | DONE | Seb | Text/font updates throughout, can benefit from styling |  | bring items above scroll if possible - to make page will look better
Promote: | Actions Menu --> "Order Report" | Bug/Improvement |  | https://design.pboffice.net/start/ | 3 |  | Ryan? | Managers? Template Usage & Orders? Report is not connected
Start | Date & Time Stamp | Bug/Improvement |  | https://design.pboffice.net/start/ | 3 |  | Ryan? | In addition to hamburger, add back into navigation to "Desktop"-only. On responsive dissappears, and office selector is preserved
Start | Office Selector | Design |  | https://design.pboffice.net/start/ | 3 | DONE | Seb | Make as concise as 3.9 - is too spread out |  | Padding, indentation. hidding/suppression of items not in results
Start | Task Reminder | Design |  | https://demo.pboffice.net/start/ | 3 |  | Ryan? | Need new feature with CTA treatment indicating, manager & agent has upcoming "Tasks" - Use existing space where "Featured Headlines" exists
Transact | Received Files | Design |  |  | 3 |  |  | Aesthetics needed, displays faxes and all incoming files |  | done
Transact | Received Files | Bug/Improvement |  |  | 3 |  |  | Changer for category is missing for office/team (personal & not)
Transact | Send to Address Updates (email address) | Bug/Improvement |  |  | 3 |  |  | Backagent host updated to Backoffice.net
Transact | Send a fax | Design |  | https://design.pboffice.net/transact/detail/property/add/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 3 | Done? | Dennis | Page needs makeover (faxes essential for banks) |  | done
Transact - (Individual) | Set Property | Design |  | https://design.pboffice.net/transact/detail/property/add/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 3 | Done? | Dennis | When click to choose "Set Property", loading property from MLS Listing (searching MLS) |  | done
Transact - (Individual) | Edit Property Page | Design |  | https://design.pboffice.net/transact/detail/property/add/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 3 | Done | Dennis | Search page needs improvement |  | done
Transact - (Individual) | MLS Search | Design |  | https://demo.pboffice.net/transact/detail/property/add/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 3 | Done | Dennis | Display of search page needs improvement |  | done
Transact - (Individual) | MLS Search Select | Bug/Improvement |  |  | 3 |  |  | On Selection of property, should take user back to detail page
Transact - (Individual) | Checklist - Due Date | Bug/Improvement |  |  | 3 |  |  | Action works, but due date does not appear on calendar In details number of items required does not change in realtime
Transact - (Individual) | History | Design |  | https://design.pboffice.net/transact/detail/snapshot/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | 3 | Done | Dennis | Overall aesthetics |  | done
Transact - Active | Snapshot | Bug/Improvement | https://demo.backagent.net/transaction/detail/snapshot/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | https://design.pboffice.net/transact/detail/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a# | 3 |  | Ryan? | Bring back "print button"
Transact - Summary | Actions Tab | Bug/Improvement | https://demo.backagent.net/transaction/detail/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | https://demo.pboffice.net/transact/detail/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a# | 3 |  |  | Quick Actions - bring (some) back to fill space. - View Snapshot - Add Note - Message Contact - Send Documents
Transact - Summary | Actions Tab | Design |  |  | 3 |  |  | Quick Actions - bring (some) back to fill space. - View Snapshot - Add Note - Message Contact - Send Documents |  | done
Navigation | Hamburger Menu - Email | Design |  |  | 3 | DONE | Seb | Overall Email aesthetics |  | done
Connect | Reservations - Property Time - Detail | Design | https://demo.backagent.net/office/resources/calendar/?id=abcc2806-562f-4a6d-b244-4f039ce0161e | https://design.pboffice.net/connect/reservations/calendar/?id=abcc2806-562f-4a6d-b244-4f039ce0161e | 4 | DONE | Seb | Update color and layout Match Legend/Key to existing calendar coloration (is from 3.9) Make better use of responsiveness and existing whitespace in desktop on right hand side Update general styling (perhaps expose Alternates List in white space?) |  | Switch calendar week view and month view (use layout like 3.9) - swap sides
Connect - Notices | Notices - List | Design |  |  | 4 | DONE | Seb | make better use of page layout & space |  | done
Navigation | Hamburger Menu | Bug/Improvement |  | https://design.pboffice.net/start/ | 4 | DONE | Seb | Connections - rename back to "Quick Links"
Promote: | Managing Products | Design |  | https://design.pboffice.net/site/control-panel/promote/ | 4 | DONE | Seb | Styling help. Is same as 3.9 right now, but plenty of room for cont updates and improvements |  | done
Transact - (Individual) | Documents - Manage & Attach Document | Design | https://demo.backagent.net/transaction/attach/? | https://design.pboffice.net/transact/attach/? | 2 |  |  | Modal needs better interface, need a second column |  | done
Transact - Summary | People | Design |  |  | 4 | Done | Dennis | Better use of white space on page - better compression Use some sort of clickable bar for "Add Buyer", "Add Seller" - too much below scroll |  | done
Transact - Summary | People | Design | https://demo.backagent.net/transaction/detail/contacts/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | https://design.pboffice.net/transact/detail/people/?17e8f22f-f10a-4fe8-82d8-b3991ce1e92a | 4 |  |  | Search Contacts modal + interaction with People screen Search on the Left side Results on the right side |  | done
Connect | Reservations Container | Design | https://demo.backagent.net/office/resources/ | https://design.pboffice.net/connect/reservations/schedule/ | 5 | DONE- SEE The URL? | Seb | Button for "Shifts Available" - update treatment as call-out and standardize with color scheme |  | done
Connect | Reservations Container - View All Page | Design |  | https://design.pboffice.net/connect/reservations/ | 5 | DONE | Seb | Make all thumbs same size |  | done
Connect - Calendar | Font | Design |  |  | 5 | Bolded - DONE | SEB | weight - hard to see |  | done
Learn: | Display (Left to Right) sliding action | Bug/Improvement |  |  | 5 | ??? | ??? | habitually looking for red, match color categories create left right slider action display week date duration in addition to M, T, W, TH....
Navigation | Quick Links | Design |  |  | 5 | DONE | Seb | Responsive positioning of Save button |  | done
Promote: | Printing | Design |  |  | 3 | DONE | Seb | 3.9 styling preserved (not horrible, works for the page, but could have a style passing |  | done
Transact | Graph - Dashboard - View Details | Bug/Improvement |  |  | 5 |  | Dennis | Graph works for now, but "Is it good for the company?"
Transact - (Individual) | Expense | Design | https://demo.backagent.net/transaction/detail/expenses/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | https://design.pboffice.net/transact/detail/expenses/?8fea672f-90cf-40f0-8cd2-7b561df5b180 | 5 | Done | Dennis | Overall aesthetics | https://design.pboffice.net/transact/detail/expenses/update/?id=2eecade6-16eb-419a-9602-0c6718ccd916 | done
Calendar | Event - Announce Event - Choose recipiencts | Design | Click to Announce Event |  | 2 | DONE | Seb
Calendar | Calendar Subscriptions | Design | profile/settings/calendar-subsciption |  | 2 | DONE | Seb |  |  | Rounded Corners
Profile | Contact Info | Design | profile/contact-info |  | 2 | DONE | Seb
Connect | Event Detail | Design |  | https://design.pboffice.net/ext/event/?390824a6-2048-43f2-b45a-00be1ba9ea6f |  | DONE | Seb |  |  | connect-calendar-share calendar
Global | Browser Error Page | Design |  | https://design.pboffice.net/help/support/browser/ |  | DONE | Seb
Calendar | Copy Event | Design |  | https://design.pboffice.net/connect/calendar/copy/?087cbd4a-ae9b-4733-a5ae-831f53a3ea2b |  | DONE | Seb
Transact | Expense - Add | Design |  | https://design.pboffice.net/transact/detail/expenses/update/?id=2eecade6-16eb-419a-9602-0c6718ccd916 |  | DONE | Dennis
Transact | Expense - Update | Design |  | Expense Update |  | DONE | Dennis
Transact | Expense - Summary | Design |  | Expense Summary |  | DONE | Dennis
Profile | Activity | Design |  | https://design.pboffice.net/profile/activity/?2866e74a-62ed-49dd-9302-87c84a4ff110 |  | DONE + 6 Tabs | Seb
Profile | Activity - Sign In History | Design |  | https://design.pboffice.net/profile/activity/sign_in_history/?30ea65fa-b2ea-4097-bf82-a7ce21a968ec |  | DONE | Seb | /activity/sign_in_history
Dashboard / Start |  | Design |  | https://design.pboffice.net/start/ |  |  |  | Mobile: The "Start" dropdown could be better centered in the navbar for mobile |  | https://drive.google.com/file/d/1oQGSMqx3xLcd1qk97B3larbcOlb1Itbk/view?usp=sharing