## SCRUM
iConnect | People | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06 | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
|  |  | Grooming |  | Internal Launch Meeting | Staging Port |  |  |  | UAT Transition to Support | Sprint Review | Sprint Planning | Grooming (Prod & Dev) | Close UAT "feature" bugs |  |  | Grooming | Production Port (HF) | Internal Launch Meeting | Staging Port |  |  |  | UAT Transition to Support | Sprint Review | Sprint Planning | Grooming (Prod & Dev) | Close UAT "feature" bugs |  |  | Grooming | Production Port (HF) | Internal Launch Meeting | Staging Port |  |  |  | UAT Transition to Support | Sprint Review | Sprint Planning | Grooming (Prod & Dev) | Close UAT "feature" bugs |  |  | Grooming | Production Port (HF) | Internal Launch Meeting | Staging Port |  |  |  | UAT Transition to Support | Sprint Review | Sprint Planning | Grooming (Prod & Dev) | Close UAT "feature" bugs |  |  | Grooming | Production Port (HF) | Internal Launch Meeting | Staging Port |  |  |  | UAT Transition to Support | Sprint Review | Sprint Planning | Grooming (Prod & Dev) | Close UAT "feature" bugs |  |  | Grooming | Production Port (HF) | Internal Launch Meeting | Staging Port |  |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review | Sprint Planning | Grooming |  |  |  | Grooming | Stage (HF) - Prod Port | Internal Launch Meeting | Integration - Stage Port | QA Complete |  |  | QA Complete | Sprint Review
| Meeting Guidance |  | Close UAT "feature" bugs | Close UAT "feature" bugs | Mid-Sprint Review |  |  |  |  | Internal Review | Sprint Retrospective | HF Port to Production |  |  |  |  | Close UAT "feature" bugs | Close UAT "feature" bugs | Mid-Sprint Review |  |  |  |  | Internal Review | Sprint Retrospective | [5 empty] | Close UAT "feature" bugs | Close UAT "feature" bugs | Mid-Sprint Review |  |  |  |  | Internal Review | Sprint Retrospective | [5 empty] | Close UAT "feature" bugs | Close UAT "feature" bugs | Mid-Sprint Review |  |  |  |  | Internal Review | Sprint Retrospective | [5 empty] | Close UAT "feature" bugs | Close UAT "feature" bugs | Grooming |  |  |  |  | Internal Review | Sprint Retrospective | [5 empty] | Close UAT "feature" bugs | Close UAT "feature" bugs | Mid-Sprint Review | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective |  | Out of sequence stage port | [5 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective | [7 empty] | Transition Meeting | [5 empty] | Sprint Retrospective
[5 empty] | Grooming | [13 empty] | Grooming | [5 empty] | Production Port (HF) | [7 empty] | Grooming | [5 empty] | Production Port (HF) | [7 empty] | Grooming | [5 empty] | Production Port (HF) | [7 empty] | Production Port | [5 empty] | Production Port (HF) | - 17 items, total remaining need estimates | [6 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port | [7 empty] | Grooming | [5 empty] | Stage (HF) - Prod Port
|  |  | Don't forget Stackify after commits! |  | Production Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | Production Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | Production Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | Production Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | Production Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.17 Stage - Prod Port |  | 10.17 Stage Port |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.18 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.19 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.20 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.21 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.22 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.23 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.24 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.25 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.26 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.26 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits! | [6 empty] | Don't forget Stackify after commits! |  | 10.22 Stage - Prod Port |  |  |  |  | Don't forget Stackify after commits!
General Announcments | Graham Cohen |  |  | Jan Team Leads: Sheetal & Frank QA: 1) Bug Prioritization - top of sprint 2) Post JIRA query links to Teams to keep handy: Production (release 10.x) & Stage ("Ready for Production - status" Support - "Hot Seat" rotation Product: Grooming Meeting necessity | Justin K. - Marketing Editor Code Review - Sheetal & Frank | Marketing Editor --> Preview in Stage by Tuesday, DE demo on Thursday ICT (RE: Ad Hoc deployments - Pankaj --> Gaurav) - Send a request & port instructions whenever port on QA or Stage Portals work (normally Frank & Pankaj) - who wants it? https://gryphtech.atlassian.net/browse/ICT-2236 (QA) to give nod - "Ready for Prod" and add to fixversion 10.12 - https://gryphtech.atlassian.net/browse/ICT-1817 |  |  |  | Changesets - add changeset, if it changes, update changeset Help Gaurav with anything needed for successful merge to stage https://gryphtechcanada-my.sharepoint.com/:x:/g/personal/gcohen_gryphtech_com/EQ19Of1N5K1En3zdHzugN8sBff6foca2afAUF1EKmiCi8A?e=BeTgJb | Marketing Editor - switch or script to enable for three regions in Stage? |  | New Fields 1) Changeset- (use this field - not new) 2) Script - new 3) Port Instructions - new Deployment stunt double needed scripts all saved to single location (TFS) REP2_REP, HITS & REMAX -organization hackathon | Start closing out UAT "feature" bugs - ensure there are none at bottom of sprint Hackathon update: One week, iConnect pilot, then other groups follow suit |  |  |  |  | Frank: iList7 ICT-2177Agent in Training: iList7 and iList10 Admin changes ICT-2218Representing agent - required field ICT-2236Portal Advertisement Tab Updates - RemaxBrazil (only) - All (3) Portals ICT-2294 - Agent in Training - SP Query needed to update all existing Dependency - Robin's iRender work ICT-2180 (2177 dependency) in front of scripts and comments, indicate whether iList10/iList7 For SQL scripts we need the folder |  | Dev to QA port - missing info https://gryphtechcanada-my.sharepoint.com/:x:/g/personal/gcohen_gryphtech_com/Ea4NSoGj8nxMsfanjorbSL8BD8tsIM3Oolwm0FdFz77VMg?e=HbKVNz QA to Staging port - missing info |  |  |  | Graham = OOO (Thursday & Friday) | [6 empty] | Yiru, Justin, Frank, Ops, Pankaj - Need to be online until we have a fully functional demo for client tomorrow by 10am - OT approved |  |  | The Scrum Alliance - Certified Scrum Master or Certified Product Owner - https://www.scrumalliance.org/community/profile/gcohen3 https://www.scrumalliance.org/courses-events/search?ctyp=Cspo&vo=true&cnty=CA&rad=30&tz=my&last=ct&pg=1 |  |  |  | EVeryone must have all environments setup on their machines - who does not have ALL environments installed - Work with OPS to get all installed locally |  | Finish up ticket - remove noniLIst users |  |  |  | Priorities: Marketing Editor - on Dev Global Referral - for HF tomorrow [ICT-2306] Referral Email Redirect - Jira (atlassian.net) [ICT-2278] -NEEDS LIST OF MISSING COUNTRIES [ICT-2423] - Jira (atlassian.net) | Estimates: 1. "Ready for Estimate" 2. "sprint" = 112 (Ready for Grooming) Out of Sprint Work 1. Always a ticket in the sprint 2. use Quick Filter to find and log opening closed, released tickets for additional work = IS ILLEGAL, NEW TICKET Dev-Beta? -modified Integration pipeline for iList10-INTEGRATION branch , port directly on TEST (Dev team must merge their sprint work to Integration branch and trigger this pipeline) | Estimates: 1. "Ready for Estimate" 2. "sprint" = 112 (Ready for Grooming) 3. quick filter 4. ADD ESTIMATE & SUMMARY (Analysis of work/dev notes/strategy) Out of Sprint Work 1. Always a ticket in the sprint 2. use Quick Filter to find and log Environment (Local) All environments, all machines | ADD Hours - 7/day - negative results otherwise | https://gryphtechcanada.sharepoint.com/sites/DevPage/Agile/Forms/AllItems.aspx?id=%2Fsites%2FDevPage%2FAgile%2FProcessGuidance&viewid=35455eaf%2D7965%2D443a%2D864f%2D0f2924ec9747 - Sprint board guidance (docs) - - Help each other get to Done (column) - If we do not understand technology, learn it - (7h/d) Helping another on a ticket? Log hours on that ticket (both persons, same ticket) - Traditional Agile - each player, takes next up in Todo - now assigning instead - WIP limits, Pileup prevention |  |  |  | Graham is OOO Single change for Design to make Need to push port to 1-3pm |  | Ipages audit trail | Production (global referral announcment on tuesday) - App store links - Google translate fix Solution: Move up Support Port to Monday? - NO Client comms - keys/label list for translations - is ok can filter by category and see necessary 1) Stage port - 40 tickets (middle of board) 2) Marketing Editor to Integration Referral manager - countries list Moldova? Error? (was checked one by one) |  |  | PRODUCT: All last minute bugs go through Graham - Bugs go into backlog, Product works with Graham to pull new item into sprint and take item out - DEVELOPERS accept bugs from Pankaj & Graham - "Just say no to bugs" (out of sprint work) - Pankaj & Graham agree on F1, F2 focus & delivery plan before & during each sprint - Feature bugs must go with the release - get those done with priority - Accountability for the Release Sprint = Feature = Release - Each sprint, 2-3 devs on one feature = list of issues - Graham's Goal - provide Carlos #hours available for feature development each sprint - will determine primary focus: | Mobile - https://gryphtech.atlassian.net/browse/ICT-2262 Alim - training, comms & orgainization (scrums forwarded) - New Sprint automation - label & comment | DH - new office integration - POST call send ilist7 office id - error - need to make call to validate and automatically integrate all office members (ilist7 - office discrepancy report, not existent in ilist10) | check with Dami for latest -Konvajs updates | Discuss new process for finished QA work - (e.g. assign to gaurav & pankaj v. unassigned) - assignment = needs work/attention, status = ready for port/transition CR to Pankaj (already underway?) https://cr.gryphtech.com/Tasks/EditMainProject.asp?ThreadID=147665 - moved to LLC UAT/Category 2022 - Global Referral Prod UA - problem follows only: CecilySell@gmail.com ? | [5 empty] | Yiru: Dev team will help on tickets on Test related to Regional Tool (6) and Proptexx (2). I will Regional Tool tickets I will make some comments for high level cases. - 17 items, total remaining need estimates - Mike's Carlos's Global referral provisioning failure notification - mobile scrum move |  |  |  | from sprint: 46 issues, "ready for stage" without a release (fixversion) - including three removed from 10.16 - not enough time to test in Stage and will go with HF | Graham to filter Christophe's board | Global referral fixes - ICT-2485 - CR remaining issue 147665 - Kevin's summary of methods to signup | 43.8 hours logged in UAT |  |  |  | StageHF Fix - 404 on global referral login Isreal - Support /Tao |  |  |  | Product - make certain there are individual tickets entered and assigned to a new Epic for iList10 Marketing on Demand - Legacy Support Product l displace existing work in the sprint - chose which items fall out Assumption - MoD work will be done for this sprint - amount of work = too much to achieve this release |  |  | Add Dami to scrum meetings | Carlos emails: Asked that Yiru enter to reconcile whether or not hase seen before Lost Souls - JIRA query - public access https://gryphtech.atlassian.net/issues/?filter=10157 | · First status of any new ticket will now be ‘To Do’ · Distinction between dev & design team ticket statuses removed by switching to – ‘In Progress’ & ‘Under Review’ · Sprint board headings are changed to be in sync 34 issues in UAT. Calculated average of ≈4hrsticket, Currently at 61hrs. 11hrs outside of our 50hr timebox. estimated 75hrs more to complete all in UAT in the sprint Decisoin: UAT vs. "iconnect improvements" | - Issues QA Submits are not UAT even if tied to UAT issue, unless managed and approved as UAT by a BA or PO (Mike & Sam) | https://gryphtech.atlassian.net/issues/?jql=labels%20%3D%20ME_MoD_Port_03302023 Need release? ICT-2478 in 10.17 Stage port - Morning Stage testing: Product (awareness), Design (konva work), Validation frank's work Plan: Email, template save/propogate, ID prod test users Monday @ low traffic in afternoon? | [10 empty] | UAT & Bugs Epics
Design | Lead | [12 empty] | OOO | [27 empty] | bug testing & review ME
[14 empty] | Focusing on REP refresh | [16 empty] | icons for Frank (MOD), 2134 - email global referral, 1874 - regional reporting, ui grid updates | [10 empty] | mockups for mobile, ict tickets, | [12 empty] | Tickets and more tickets: Region fields (new), ICT-2111, 2106, 2107 | iconnect page - + "...and territories" must be added (legal compliance) |  |  | Viking Product mockups Marketing Editor - completing showstoppers c21 templates |  |  |  | Sonia - will get running on templates C21, mocks, viking, rep sites... long list (templates, "short-list" - addl. product review necessary?) |  |  | Dami will work the Z positioning issue - days work | Frank: Proptexx design icon: ICT-2494 |  | 5 tickets - ICT-1749 - regional tools integration - christophe to send graham tix list | [10 empty] | 1874 |  |  | ICT-2509 ICT-1756 - brochure 1526 - global search enhancements | Provided MoD documentation Dami started Marketing Editor timeboxing work today thumb is chosen - is chosen from iRender |  |  | Generate Bochure - 1756 Global Search enhancements 1526 |  | Regional Dashboard review - larger numbers |  | Rebuild CSS on 10.17 for stage port Need regional dashboard work back (1 day) | [5 empty] | regional dashboard will be done by morning for port to Stage |  |  |  | OOO | OOO | OOO | OOO | OOO
|  |  |  | ICT-1941 - add any/all "Layout Editor" work performed | ICT-1941 - add any/all "Layout Editor" work performed | ICT-1941 - add any/all "Layout Editor" work performed | [38 empty] | Templates for Marketing Editor (justin working on scripting to move finished templates between environments) | Logo update - 2423 - tomorrows production port!!!! |  |  | Support port blocker - small design fix | [6 empty] | (Local) ME - template edit and save - needs to be fixed to continue test Dami's updates to DEV (Frank to assist) |  |  | Need to test merge ME updates | ME Bugs - Errors on local (rep2 geo country list get - missing sp), Layout editor bugs, | [29 empty] | regional dash? |  |  |  | Regional Dashboard | [6 empty] | Diego/Frank Dashboard assistance - For ALL dashboards: 1) make width of region selector as wide as longest name 2) make Y axis taller 3) Properties: "current sale inventory" move down below - give graph full width of box 4) graphs in side by side divs do not align within box | [6 empty] | LAR
Designer
[87 empty] | timeboxed marketing editor work |  | editing text on saved templates | [7 empty] | Will estimate B's and C's
[87 empty] | Console errors on branch in use | [17 empty] | needs dev work to move a few items forward for Layout Editor
Product | Product | [45 empty] | refine ICT-2367 - category selector
[87 empty] | Meeting with Graham JIRA premium |  | not in attendance | not in attendance | not in attendance |  |  | All templates will eventually need to be exported - in image & PDF (same logic in REP)
[47 empty] | ICT-2084 ICT-2196 ICT-2045 | [39 empty] | https://gryphtech.atlassian.net/browse/ICT-2125 |  | https://gryphtech.atlassian.net/browse/ICT-2543
Deniz Karaaslan
Product
[62 empty] | Meeting with Robin - cropping function image uplaoder eSignatures query - chen - extend duration to include Jan/Feb 2023 - (already done and added to ticket) - RTL - tickets added | [6 empty] | Tracking invalid logins | [5 empty] | Get ticket to sprint - display currency with formatting (decimals & dollars) - datahub | [7 empty] | Marketing Editor work Jane & DH Proptexx follow-up | [5 empty] | Today we stop on UAT (including macro office) | macro office epic proptex meeting for Friday 9AM | [10 empty] | Reminder: Ready for Grooming/Ready for Estimation - DONE |  | Reminder: Ready for Grooming/Ready for Estimation - DONE
[42 empty] | Needs ICT-2306 |  |  |  |  | proptexx assigned to you, why? 2216 ICT-1276 ICT-2251 ICT-2296 ICT-2331 ICT-2347 ICT-2377 | [7 empty] | Global referral messaging translations - Pankaj (sent to Sam, imported on Stage) | Client Contact/Label - move to "cooperation mgr." - Defect Duplicate emails - Defect |  |  |  | Remax isreal - ilist10 issues - UAT issues - functionality in RTL - discover RTL tickets? - needs QA work on RTL - Grooming sessions | [9 empty] | https://gryphtech.atlassian.net/browse/ICT-2485 Carlos: “We are not asking them to make any changes to the file and will use any email address they provide us” |  |  |  |  | Datahub - formatting (transaction (display) vs sent to DH) | [13 empty] | Mike to setup meeting with Proptexx - (thailand hrs - friday morning) |  | Removing iConnect improvement issues for port - marketing demo | [5 empty] | Needs list of ilist7 regions with datahub enabled to enable in list10 | will check with Proptexx |  |  |  | Do not work on UAT today - will prioritize | Proptexx - reconcile ask v. delivery - is not what was desired. |  |  |  |  | DH cannot report/test - any payment added is april, but current payment is march - all will be in April - payment date validation issue?
Product
[42 empty] | PDF generation for energy rating | [27 empty] | Area Guides comin' soon | [16 empty] | ICT/Web thumbnail resolution on mobile |  | no update | no updates
ICT-2378 - brochure - energy rating
Development | Dev Lead | [33 empty] | SSO fixes, wont' work w/o user and password |  |  | Global referral SSO, should go to prod today, email for global referral, REST job not working |  |  | Yesterday: unexpected port, & stage port for Yiru, deep linking for nonilist users - | [7 empty] | dev-beta is working!! | [33 empty] | multiple server from load balancer = stage impersonation token saved in memory cache - 500 error | ticket for translations - global referral translations |  |  | Dev work ported to QA | [20 empty] | Stage port -
|  |  |  | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO |  |  |  | Global referral issues - gateway changes |  |  | proptex items -= design changes - support port |  |  | SSO - production work |  |  |  | middle of the board and marketing editor |  |  | Global referral tickets |  | Port, Code Review, setup dev-beta |  | dev-beta scripts run the GR make-live script in production |  |  |  | Champions the Sprint Retrospective, today! (graham is OOO) |  | Sprint work (Global Referral: translation work, working another list today) | Stage port for QA (including google translate fix) |  |  | STage port on Friday ME to integration - after latest changes | "display all listings" RM Italy - ICT-2375 Production port in the AM | Production issue - existing issue must be fixed before port - GR-loading countries list (latency issue) | Performed recommended steps for reverser merge with ME & integration. | Board work and organization, worked with Mike & priority for the smaller items | [5 empty] | Estimates Datahub testing / transactions Proptexx needs email | DH testing coordination, pending tickets on board (buyer job) Proptexx email sent with proposed steps |  |  |  | stage port to ready for production port tomorrow Language translation issue for regions / global referral (translations wrong for language) | Porting, escalation tickets from global referral (invalid email address) | Mike for global referral meeting Stage port | Stage port today | [5 empty] | Proof GR situational/guidance doc for accuracy - Kclews/RobS | Support work - Chen - AGent in Training work Macro office - work/Tao |  |  | Dami - editor work? | Datahub - billing period update - ready for test | run ME prod scripts |  | port - marketing demo - 10.17 proptexx discussion - timeline requested from PT team - 13th to Stage |  |  | Production port tickets to clean for review tomorrow | https://cr.gryphtech.com/tasks/Task.asp?ThreadID=147693 |  | Stage Port '3 regions for DH go live in Stage |  |  |  | Staging Port, Ticket allocation to QA, Estimation |  | Production port, SP language/listings fix, UAT prioritization | Production issues, stage port (sam's issue same issue as yesterday)
[45 empty] | Meeting with Datahub - Mike | dev work required on datahubs side after meeting |  |  | need porting ticket, dev-beta | [6 empty] | ICT-2460 needs verification on Test |  |  |  | ICT-2126 micro opt out option - no code in ilist10 for microsite control - dependency - blocking issue |  | Needs smoke test in QA for ME editor | [6 empty] | 2258 - Referral direction b/w ilist and non-ilist. Archive all regardless of status "sending is non-ilist OR receiving is non-ilist" | [6 empty] | Transactions module to Stage? (1/2 finished to Stage, need DH advance billing months) - unpdate sp's for formatting - | Google tag manager = ilist10 (meetings with Ops/support) - MIght need more time with the ticket - might need more Google accounts | [6 empty] | Needs to speak with Mike about CMA ticket |  |  | Proptexx |  | Hostname display: regadmin, superadmin | [11 empty] | Portugeese listing load with language selected
| Sheetal Ahuja |  |  | All Active iList Regions except CCA (Caribbean and central America) and show non lists regions -- Working Send the no. of records return on PRoduction for No response for X days - Send data in Team - To Deniz and Carlos. | All Active iList Regions except CCA (Caribbean and central America) and show non lists regions -- Completed ICT-2261 Global Referral Release - REP2 DB - Deletion of all Non-iList Users -- Working | refectored SQL script to remove ilist users | Yesterday - Production scripts 2198, 2199- Working |  |  | Production scripts - Updated the scripts. 2198, 2199- Global referral creation issues - Completed |  | 2272 - Referral record missing when send group referral across different country -- assigned to Yiru 677 --Contacts - Add new contact save button becomes enabled after saving -- Completed ICT-2277 - missing office staff name on " Adding on behalf of" label - Working ICT-2284 - Referral Defect (Staging) - Exception when a Referral is Opened --Completed | ICT-2277 - Global referral - missing office staff name on " Adding on behalf of" label - Completed ICT-2282 - Global referral - displayed receiving agent name instead of Sending agent name on behalf of label when office staff edits -- Working | YESTERDAY: ICT-2277 - missing office staff name on " Adding on behalf of" label - Fixed ICT-2282 - displayed receiving agent name instead of Sending agent name on behalf of label when office staff edits -- Fixed ICT-808 - Potential Buyers Grid Scrolling Issue - Completed ICT-2274 - New group referral- attached document is missing for 1st & 2nd agents -- Fixed |  |  | ICT-5 - Contact Import - keep failing the import - Fixed ICT-1272 - Contact Avatars - contacts missing initials and colours -Working | ICT-1272 - Contact Avatars - contacts missing initials and colours ICT-18 - Public Contact Issues. ICT-1527 - Timebox: Listings Map view POCs -- Working | ICT-1527 - Timebox: Listings Map view POCs ICT-22 - iList 10 - Contact Details - Motivation ; Time Frame ; First Time Buyer fields value is not getting preserved ICT-542 - Switzerland CRs - Selected all contacts count is incorrect based on lead source category | ICT-2015 - Changes to Translation Tool | ICT-2015 - Changes to Translation Tool Worked with Uma to check Mobile translations Worked with Uma on how to test disable agent task and working on the isswue to fix it. |  |  | Support ticket - Did code review - iFranchise - 147250 2303 - Contact issue FIxed the bug - Disable agent |  |  | Ifranchise support port - 146617 2278 - Discuss with Mike and Frank - Need to talk with Robin today. Will start work on this today. Working on stage issue - QA reported for group referral. | Yesterday - stage group referral is not getting created - Fixed 2278 - Discuss with Rob. ICT-2278 - UAT - Global Referral Countries list - Working |  |  | ICT-2278 - UAT - Global Referral Countries list - Working | ICT-2278 - UAT - Global Referral Countries list - Working | ICT-2278 - UAT - Global Referral Countries list - Completed - Tao need to sync. data to REP2 CT-2302 - UAT - Referral Manager -Working ICT-2315 -Listings Map view (syncing data issue: https://gryphtech.atlassian.net/browse/ICT-2337) |  | Late port last night (2 hours) |  |  | Contact issue (3 issues)
[14 empty] | Today: ICT-5 - Contact Import - keep failing the import - Working |  |  |  |  | ICT-2015 - Changes to Translation Tool -Working |  | Code Review, pls - https://cr.gryphtech.com/Tasks/EditMainProject.asp?ThreadID=147250 | [6 empty] | ICT-2278 - UAT - Global Referral Countries list - Working | [6 empty] | ICT-543 - came back from QA Map task |  |  | Mapping issue
|  |  |  | Carlos response for display ilist/non-ilist region |  |  | Mobile team -- Need to add the category for mobile so that they are see mobile translations on the UI. - updated to test and stage env. | [6 empty] | 2285 - critical issue - referral manager - assigning to Chen (blocked by other existing, critical work and environment install issue)
| Dev | [11 empty] | ict-2252 | ICT-1224 - took a look and re-reouted for 2007 (2 days work) | [23 empty] | excel export for listings on sale | [45 empty] | ICT-2533 - UAT - Decimal values issues | [12 empty] | JS error agent edit profile Another..
|  |  |  | ICT -125 | ICT-2260 - Regression - Users list page - Region admin users missing | ICT-2260 - Regression - Users list page - Region admin users missing - Done | ICT - 2046 - iConnect Redesign M3 - Listing Search- Map View 1224 |  |  | ICT-1224 - Agent Rating - Agent Rating Report - RTL Issues - dev see comments | ICT -2240 - Event appear on the previous day than actual day when add agenda in past | ICT -2240 - Event appear on the previous day than actual day when add agenda in pas ICT -2252 - Tested on test env and works , confirmed with qa ICT - 2007 - had a meeting with frank for a potential solution and with mike for proper acceptance criteria | ICT 1224 - produced report to see the issue with help from chen ICT-542 - Found some issues with the page in question, had a talk with yiru to inform of these issues ICT -2007 - started working on it after getting go ahead from graham | ICT -2007 - price field formatting globally - continue working |  |  | ICT -2007 - price field formatting globally - continue working | ICT -2007 - price field formatting globally - continue working | ICT -2007 - price field formatting globally - wrapping up | ICT -2007 - price field formatting globally - discussed with sheetal for best approach to apply solution ICT-2104 - Contact display name format - had a meeting with frank, made the setting work, it is working but there is some cache that is needed t be cleared to have it in effect ICT-2126 - Microsites - Opt out option - chatted with chen and mike that regional setting required is missing so on hold Dug up some changesets to fill in the stage port excel sheet | ICT -2007 - price field formatting globally - discuss with mike to apply the solution by modules so it does not impact the whole application at once ICT-2104 - Contact -display name format - finalize it |  |  |  |  | ICT -2106 - On Sale properties settings | ICT -2106 - On Sale properties settings | ICT -2106 - On Sale properties settings ICT - 2107 - On Sale - new fields on property details ICT 2240 - fixed for event drop and event resize from calender ICT - 2007 - added and tested more places |  |  | ICT -2106 - On Sale properties settings ICT - 2107 - On Sale - new fields on property details | ICT - 2107 - On Sale - new fields on property details - fields exist in ilist7 - checkilogic and have it in list10 | ICT - 2107 - On Sale - new fields on property details - did the stored procedured and backend changes, working on ui | ICT - 2107 - On Sale - new fields on property details - did the stored procedured and backend changes, working on ui | ICT -2106 - On Sale properties settings |  |  | ICT -2106 - On Sale properties settings |  |  | ICT-2240,2397 - PAst events disppearing ICT-2106 - Date not appearing when come to setting page but appearing on reload, also need mike's approval | Finished properties settings, ICT-2111 - best deals |  |  | ICT-2111 - best deals ICT 2007 - UAT - CMA - Add formatting to min/max price fields |  | ICT-2111 - best deals - Almost done ICT 2007 - UAT - CMA - Add formatting to min/max price fields ICT - 2397 - Is done under different changeset , will update | ICT 2240 - Added support to change the view values on event drop and event resize and preserve agents, listings ICT - 2111 - Worked on the use case for agent impersonating as office admin | [6 empty] | ICT-2110 - For Sale - DONE ICT-2007 ICT-2301 -DONE | ICT-2007 - CMS ICT-1985 - Preferred Language - Display Regional Language first as default |  |  | ICT-2007 - Added the new directive everywhere, in middle of testing(rectifying decimal conversion for different cultures in multiple places) also made CMA improvements (field name change, removed field directive where no field setting, condition for regional setting loaded, fixed the regionalsetting get) | [ICT-125] - lead pipeline chart | [ICT-2463] - Jira (atlassian.net) - referral price range is whole numbers | global referral - price range ICT 2481 - RA not able to view profile | ICT 2474 - Global Referral- Goggle translation drop-down missing on history table for OA/RA users ICT - 2463 - PRICE RANGE | [5 empty] | [ICT-2471] - Jira (atlassian.net) Also, best eal appearing twice | [ICT-2427] UAT - Listing address saved in hebrew displays in english - Jira (atlassian.net) |  |  | ICT-2015 - Changes to Translation Tool ICT -2496 - UAT-Global Search-Price values are still in the format of local language after switching to English | ICT -2496 - UAT-Global Search-Price values are still in the format of local language after switching to English | ICT -2496 - UAT-Global Search-Price values are still in the format of local language after switching to English | Currency formatting applied everywhere. | ICT- 1874 Regional Reporting - Related Income grids - UI Updates |  |  | ICT- 1874 Regional Reporting - Related Income grids - UI Updates ICT-2526 - Listing Detail page-Incorrect validation message showing ICT-2525 - UAT - Property - Commission Details: price format issue with input values |  | ICT-2525 - UAT - Property - Commission Details: price format issue with input values | ICT-2533 - UAT - Decimal values issues | Transmittal report formatting issues - must apply currency symbols for price |  |  | Transmittal report formatting issues - must apply currency symbols for price Decimal values next | ICT-2533 - UAT - Decimal values issues ICT-1783 - UAT - Remax Poland Wants to See the Currency Symbol After the Amount | ICT-2533 - UAT - Decimal values issues 'ICT - 2488 - UAT - Colors of the Legend and Graphs Ate Not Consistent | ICT - 2570 - Security - Truncate Hostname Display - RegionAdmin & SuperUser noCr: Office dropdown show | ICT -562 Feedback - Agenda - Translation issues ICT-2585 - UAT - Listing Images not showing on website |  |  | ICT-2585 - UAT - Listing Images not showing on website | [6 empty] | Commission currency symbols | ICT-2649 - UAT - JS errors - Add Property from Edit Contact page ICT-2649 - UAT - JS errors - Add contact task from Edit Contact page | ICT-2639 - Region Dashboard - number/price formatting | not in attendance | Needs work |  |  | translation issue |  |  | ICT 2706 - 'Step 2 - Expose office selector in the following places
[41 empty] | Mike's approval on ICT-2106 |  |  |  |  | https://gryphtech.atlassian.net/browse/ICT-2046?filter=10134 - blocked from Mid-Jan | [9 empty] | discussion with Mike/Carlso for 1985 | [5 empty] | decimals on slider - dollars | [13 empty] | 2 types of formatting 1) filtered FE, back-end - need to address
| Senior Dev |  |  | Today: Marketing editor regional languages for Name/Description. |  | Spoke with Justin, RE: ME |  |  |  | Can now load categories |  |  |  | Yesterday:CR147010 Tunisia text/list label translation list from prod --from Mike. Prod Issues on regionalized lookup for the regions supported language is not 'en-US'. Marketing editor on loading existing template for Edit/Save |  |  | Yesterday:Ilist7 Porting folder, Portal porting setup/scripts, marketing edit saving Merged Justin & Franks work to Dami's branch, once Dami reviews, merge back to F & J's (process this way because of DB updates) - will not take long | Yesterday: marketing editor save/save as copy | Demo-ed to Marketing Editor team, need help impersonate and permissions restore on return to super admin | Yesterday: Porting and Porting issues fixing on prod. Finished Marketing Editor template type filter/ load existing template languages for name/description/subject/email content. | Yesterday: Marketing editor Cover image upload/for new/edit template | [5 empty] | Yesterday:Marketing on demand- image download, PDF share | Marketing on demand PDF share (issues on very big PDF file after created from image--fixed) |  |  | Yesterday: PDF Download, share/download code clean up, email logic | Marketing on demand PDF/Image template share/download and code cleanup. email step | email logic, then emergency merge/port to dev for demo | merge fields listing Tilte/Description, fixed merge fields value and label for Bebs/bath/total sqm. discuss static upload image. | Yesterday:Image/PDF templates on Email logic, stage/prod porting issues fixing - (3 hours) |  |  | Image/PDF templates Email |  |  | Yesterday:ICT-2361 loading static uploaded image for Marketing on demand. ICT2358 Marketing editor saving issues on second clicked.ICT-2355/2357 updated text and sent to design team to review | Yesterday:ICT-2353 Marketing Editor Preview Html content. Stage global referral find agent performance issues fixing |  |  | Yesterday:1.new changingset merged from dev-MarketingEditor (changing set 19809 to 19939) to iList10-INTEGRATION-Marketing 2.Marketing on demand image/pdf template for share/download not loading --fixed the last merging issues. 3.Property details loading issues on property details page-- fixed | yesterday: 1.iList10-INTEGRATION-Marketing dev porting fixing. 2.Scripts added regional setting "Pages.Marketing" and "Pages.Marketing.OnDemand". 3.script to add agent/office admin to have role level permission for "Pages.Marketing" and "Pages.Marketing.OnDemand" 4.Code changing for super admin has "Pages.Marketing" permission all the time 5.ICT-2375 iConnect listing search parameter @Lotsize issues fixing. 6.Extract Global referral translations | yesterday:ICT-2444 iconnect changing:Global Referral application filter by name ICT-2278 iconnect changing for new intranet users | yesterday:QA on Test: ICT-405 good to stage ICT-542 good to stage review: ICT-2432 and get prod version splistingsearch and apply changing on new version ICT-2208 Migrate/remove htmltoPDF function at GT --removed "html2PDF" from iList7 app.config --OPs turned off gthtml2pdf and will monitor the status. DEV-Beta DB Migration issues fix(inluded missing .resx files) | test on test for DH update/terminate/reactive profile: ICT-921,ICT-1368,ICT-1367,ICT-925,ICT-1369,ICT-928 |  |  |  | vacation | vacation |  | Yesterday: 1.ICT2460 goolge translation on global referral comments. 2.Page js error fixing on referral details page 3.ICT2458 new global referral choose agent and findAgent page, country required validation. 4.ICT2290 Global referral report(scripts to enable report Success Rates under Coorporation Manager category) |  |  | Yesterday:ICT2246 marketing editor saving issues fixing.ICT2290 Global referral report | Yesterday: ICT2375 iconnect property search. ICT2290 Global referral report | Yesterday: ICT2314 Listing Image Crop image Url fixing.ICT2478 Marketing Editor #1,2,3,6 fixing. | Yesterday:ICT-2216 Proptexx - Replace Restb.ai, create job to call API | 1.Emailed to Proptexx and they promised to do change to support image url name with "-". 2. discussed with robin for ilist7 image resize and Crop. 3.ICT2216 proptexx job and suggguests mapping. |  |  | Yesterday: ICT2216 Proptexx mapping/job. | Yesterday: ICT-2216 proptexx ICT-2424 CMA print js error. |  | Yesterday: ICT-2499/ICT2497 referral report and export PDF changing ICT-2492 update report list translations issues fixing ICT-2402 Listing Activity Report code merge from Rep.General (1.Generate Activity Report popup. 2.preview popup. 3.Merged and Created Endpoint for :GetListingActivityReportDetail/Download PDF/Send 4.Merged translation .xml file) | Yesterday: ICT-2402 Merged and tested code from local for Listing Activity Report ICT-2402 proptexx/restB.ai QA on test for iList7 and iList10 ICT-1224 AgentRating report RTL report/PDF fixing. |  |  | Yesterday:ICT-2497 Referral report changing for report/PDF to fix the size better ICT-2315 Listings Map view mapbox tiles with language changing.need discuss. #Prod issus to trace and more indexes created for sproc GetLookupListMultiple (need Task# to add nolock) | Yesterday: ICT-2505 Global Referral Registration Log | Yesterday: ICT-2339 Region Dashboard New page/views/app service ICT-2341 Period Selector | Yesterday: ICT2340 Regions Selector ICT2342 Regions Currency List | ICT2345 Agents ICT2344 Offices ICT2346 new leads |  |  | ICT-2346 New Leads 1 ICT-2385 Leads Source 1 ICT-2381 Website 1 ICT-2382 Leads Pipeline 1 ICT-2384 BuyerMatch 1 ICT-2383 commission |  | ICT-2386 region dashboard offices grid | Yesterday:ICT-2386 region dashboard offices grid.ICT-2387 office dashboard changing | ICT-2387 office dashboard changing (create directive for region/office/agent dashboard) |  |  | finished :ICT2387/2388 office/agent Dashboard changing. added new directive for regions /offices/agents dropdown | Finished ICT2545 added "EmailTemplate.ListingJustListedPromo" for one listing (code changing). added "EmailTemplate.AgentPromoSellingOne" without listing. ICT2546 Multiple listings email | ICT 2546 Multiple listing email ICT 2544 |  | merge field (only office phone) email templates - tested listing summary - 4 image questions? |  |  | MOD stage/prod setup, prod issues fixing, testing on prod. ICT 2589 agent image changed to use Large.ICT-2548 copy email templates |  |  | ICT-2619 Marketing --9 listing images to merge and load default if not exists --new field listing parking --set lenght limitations on listing description ICT2620 Region dashboard added to get “Agent“ and “Office Admin“ for agent dashboard agent dropdown ICT2629 Region dashboard - Properties Widget - number of 'New' listing is empty fixing |  |  |  | ICT-2630 region dashboard roll back 21324 noCR - Fix for current and previous month filter( broken logic) and fixing for current month chart data ICT-2338 agent dashboard added to show for agent dropdown on condition for parent container ICT2615 Marketing ON D performance | Performance issues - image PDF template (cannot do sub-second, rather 5-6) | ICT2575 currency symbol for BM/MA/office dashboard/agent dashboard fixed listing map view error when has listings in foreign countries | Continue | ICT2407 List of Activity Stats ICT2408 LAR preview/pdf/email |  |  | ICT2409/ICT2410 1 or multiple owners ICT-2411 no owners ICT-2412 Listing where owner(s) has no email address ICT-2413 LAR - Send - Warning message when owner(s) have no email address ICT-2416 LAR - PDF hide footer ICT-2417 LAR languages
[5 empty] | Marketing Editor - migration, created new table to save | Marketing Editor, Portals ICT-2236 - Need aadditional time to setup templates for carlos demo in old ME on 01/12 | Yesterday: ICT-2236 portal change for macro office url Done for iList7 and iList10 Marketing Editor template admin for super users |  |  | Marketing Editor - Menus - template admin Edit template |  |  | Yersterday:Marketing on demand scripts/set up / on stage | Today: Save/ save as copy template |  |  | today: marketing editor saving copy | today:marketing editor to edit the existing tempate coverimage/langugages/categories groups Will check in latest changes, onto Dami's branch, Christophe working on CSS changes for Dami's machine to work with changes Fields between LIsting agent & AGent info need to be updated | Filtering, and Dami branch | Today:Market editor load existing image cover | today:ICT 1453 flip the icon for print/image. Category templates order on order/Name |  |  | Meeting at noon to coordinate remaining ME items for review tomorrow Language work on the templates |  |  | today:marketing on demand --pdf share/download | today: 1.PDF Download, 2.Email Logic changing |  |  | Email logic for new template, fixing broken js | continue on Marketing on demand email step | Merge field check/audit - title, description, Upload file - investigation (can use blog function for images, tags, attributes) | Image/PDF templates on Email logic | Today:get new branch iList10-INTEGRATION-Marketing and continue on Image/PDF templates on Email logic |  |  | Image/PDF templates Save as My templates |  |  | today: marketing editor preview html contents. | merge branch - baseless merge from last week with (file by file) |  |  | Email templates - Permissions |  | 0.5 - 1.0h needed with Robin proptexx |  | finish out QA, create bugs, update status | [5 empty] | Today:1.cooperationRequest page vm.uploadSelectedDocument is not a function js error fixing 2.ICT-2460 Global referral comments re-ordered while applying google translation | today:ICT2290 Global referral report ME bug: |  |  | today: ICT2375 iconnect property search. ICT2290 Global referral report | Today:.ICT-2314 listing images Crop fixing.ICT-2216 Proptexx - Replace Restb.ai | Today:ICT-2216 Proptexx - Replace Restb.ai | Today:ICT-2216 Proptexx - Replace Restb.ai, call API "detect-room-type" and features:"detect-material","detect-building-style" | Today: ICT2216 Proptexx mapping/job. |  |  | Today: ICT2216 finish up Proptexx |  | Proptex testing Syn with Mike - proptexx service needs - "Jay" email with list of items needed | Today: ICT-2402 tested and can show 1.Generate Activity Report popup. 2.preview popup. | Today: ICT-2497 Referral report changing for report/PDF to fix the size better ICT-2315 Listings Map view |  |  | Today:ICT-2505Global Referral Registration Log | today: ICT-2338 Region Dashboard | Today: ICT-2340 Region Selector ICT-2342 Currency Selector | Today: ICT2345 Agents ICT2344 Offices | ICT2346 new leads.ICT2385 leads source.ICT2380 Properties |  |  | today:ICT-2383 commission ICT-2380 Properties | ICT-2386 region dashboard offices grid | ICT-2386 region dashboard offices grid ICT-2387 office dashboard changing | Today:ICT-2387 office dashboard changing ICT-2388 agent summary page changing | ICT-2388 agent summary page changing |  |  | ICT2545 MOD single listing Email step for email templales | 1.ICT2546 MOD Multiple listings email 2.ICT2544 MOD Emails for new layout on PDF and Image templates | ICT2544 email step for "Image"/"PDF" template to save template | Region templates |  |  |  | ICT-2548 copy email templates to fixing the coverimage/translations |  |  | ICT2630 Commission box issues on test |  |  |  | ICT2615 Marketing ON D performance | Performance: Email templates | Today: ICT 2406/2407 LAR | Today: continue: ICT 2406/2407 LAR | Continue LAR |  |  | LAR 2414 Footer and need Prod
|  |  |  | translation: New unique values required for email description? |  |  | today:Marketing Editor template admin for super users | [13 empty] | Need CSS to work on his machine (Dami) | [23 empty] | Marketing Editor (agent v. region permissions) - might need to update - Product? (how it shoud work) | [14 empty] | Marketing Editor - assistance with Christophe |  | "image file name" not supported? char discrepancy - investigating | [24 empty] | Christophe to perform design review | Marketing Editor - on Stage (discussion to get to Design ASAP, on most recent) | [5 empty] | error on listing summary 4 image template - must update image & translation (kw content) | [13 empty] | footer link subscribe - new or follow ilist7 - remax website
| Senior Dev |  |  | Today will work on iconnect soft launch porting folder will work on ICT-227 | Yesterday: ICT-227 referral fee function - agreement detail Done | Yesterday: ICT-2263 - done ICT-2177 - done ICT-2029 - transaction reporting | Yesterday: ICT-2031 Done ICT-2029 |  |  | Yesterday: worked on ICT-2029 worked on ICT-2216 |  |  | Yesterday: ICT-382 Done sold property shouldn't show restb.ai suggestion ICT-2192 Done ilist7 transfer agent not change rep2 db ICT-1976 | Yesterday: ICT-1976 Agent x-fer - Done ICT-2177 agent in training support test ICT-2273 |  |  | ICT-2273 Done tranfer agent |  |  | ICT-2293 Done(LQA menu) ICT-2249 global search filter change | [11 empty] | ICT-2333 update datahub info in DB(Done) ICT-2029 regional report(need check with Mike) ICT-2314 turbo uploader image | Yesterday: ICT-2314 turbo uploader image (Done) ICT-2285 (Done) ICT-2029 (Done) | ICT-2030 -transmittal reporting | ICT-2336 (HF) non ilist region login in iconnect auto create user in ilist10, auto redirect to global referral in ilist10 ICT-2030 -transmittal reporting |  |  | ICT-2030 -transmittal reporting |  |  | ICT-2378 new ticket for update ilist7 listing generate doc and pdf show energy part logic looked into stage port issue | ICT-2378 Done ICT-2030 still get issue from datahub side and response to Pankaj stage port issue |  |  | ICT-2306 Done | ICT-2421 ICT-2249 ICT-2389 ICT-2423 | ICT-2306 done ICT-2378 done ICT-1724 done | work stage port issue analyze work on ICT-2445(#2,#3 need Mike create new ticket to check in code) ICT-2030 | test: https://gryphtech.atlassian.net/browse/ICT-1363https://gryphtech.atlassian.net/browse/ICT-916https://gryphtech.atlassian.net/browse/ICT-1361https://gryphtech.atlassian.net/browse/ICT-1362https://gryphtech.atlassian.net/browse/ICT-938 | [5 empty] | ICT-2378-fixed issue esignature script ICT-2031Regional Reporting - Making changes to the Transmittal report ICT-2027 Regional Reporting - New tab: Transmittal Report (contents) ICT-2275 Regional Tools Integration - DH/iFranchise - related Income bug ICT-929 analyzed code | 929- datahub x-fer agent |  |  | ICT-2279 Global Referral: Duplicate Email Issue ICT-929 Transfer Agent/Office Admin | ICT-2372 Representing agent change for Brasil (Important - Hotfix) ICT-1783 Remax Poland Wants to See the Currency Symbol After the Amount ICT-2470 | ICT-2187 Regression - Global referral - RA user - Status buttons ICT-2190 Regression - Global referral - RA user - Edit icon should not be visible ICT-542 Switzerland CRs - Selected all contacts count is incorrect based on lead source category ICT-2251 Regression - Region admin unable to edit Buyer match | ICT-2390 iList API - New endpoint and Integrator ID Proptexx | ICT-2390 Done ICT-2339 Global Referral - Non iList user account creation - 404 error on initial login - Refer to ICT2336 |  |  | ICT-2339 Done ICT-2475 ICT-2137 Done ICT-2424 Done |  |  | ICT-4 Done ICT-12 Done ICT-2258 | ICT-2030 worked on the popup message ICT-2027 discussed and tested |  |  | (ICT-2027,ICT-2030 ) test datahub check if they can support decimal fix multi agent and both side commission issue | (ICT-2027,ICT-2030,ICT-2031 ) implement the separate the listing and selling end implement show active and inactive integrate anget in the list | ICT-1724 ICT-2258 ICT-2489 | ICT-2473 ICT-2514 ICT-2027 | ICT-2343 GTM Tracking ICT-2489 fixed class issue ICT-2473 |  |  | ICT-2027 discussed with pankaj, rollback ilist7 SP, created new SP for ilist10, and updated ilist10 code ICT-2382 ICT-2343 |  | ICT-2500 Change Intl Sales Associate ID to Enterprise ID | ICT-2515 Updates to Office Staff Profile |  |  |  | ICT-2537 Regression - Property - Validation message for Representing agent ICT-2515 Updates to Office Staff Profile | ICT-2541 Regional tools integration - RE/MAX title issue ICT-2512 UAT - Country list for GR and GS | ICT-2512 UAT - Country list for GR and GS ICT-2541 | ICT-2541 Done ICT-2560 Done | ICT-2027 |  |  | ICT-2027 Done ICT-928 Reactivate Profile(done) ICT-2560 Done |  |  | ICT-2604 Agent In Training - SSO from Max Centre - Update to Agent Profile Unchecks AIT Flag ICT-2576 analyzed the root cause ICT-2610 & ICT-2608 office staff change ICT-2579 contact communication issue analyzed |  |  |  |  | ICT-2562 Done ICT-2638 Done ICT-2642 Done | ICT-2651 Done ICT-2647 Done ICT-2404 | ICT-2403 LAR Report Screen ICT-2404 LAR - Subject ICT-2405 LAR - Title, Address & Photos ICT-2656 UAT - BM map search not working | ICT-2677 CR - 147696 - RX Brasil - ImovelWeb -Add Super Highlighted option - Listing adv tab for ImovelWeb ICT-2678 CR - 147795 RX Brasil - PadraoiList, FormatoPadraoGroupoOLX- Implement highlights options as similar to GroupoOLX and include the same in feeds ICT-2651 Regional reporting - Transmittal report button Logic - see error after clicks on Transmittal report button ICT-2611 Global Referral - Card displayed on iConnect landing page for iList user |  |  | ICT-2611 Done ICT-2692 Done ICT-2690 UAT - Region admin user disappeared from iList 10
[5 empty] | Today: ICT-2263 - agent title issue ICT-2177 - stored proc issue ICT-2029 - transaction reporting | Today: transaction reporting ICT-2031 ICT-2029 | Today: ICT-2029 ICT-2027 |  |  | Today: ICT-2216 analyzed proptex replace restb.ai |  |  | Today: ICT-1976 ICT-2273 | Today: ICT-2273 |  |  | Today: ICT-2285 - Yiru referral view profile - bad url ICT-929 - timebox ifranchise agent xfer | OOO | OOO | ICT-2296 iList7 prod issue send to Mike confirm ICT-227 ilist10&ilist7 create referral test issue ICT-2208 Timebox for htmltoPDF analyze ilist7 and iconnect | OOO |  |  | Off this week? | OOO | OOO | OOO | OOO |  |  |  | ICT-2314 turbo uploader image (Done) ICT-2285 (Done) ICT-2029 regional report(continue working on this after get reponse from Mike) | Today: ICT-2030 -transmittal reporting | ICT-2030 -transmittal reporting ICT-2336 non ilist region login in iconnect auto create user in ilist10, auto redirect to global referral in ilist10 | Continuing work ^^ and another reporting ticket |  |  | ICT-2030 -transmittal reporting (debugging because of new logic) |  |  | work on with pankaj to fix stage port issue | ICT-2306 - GR - is not a four hour ticket, as per estimate entered |  |  | ICT-2421 datahub call log response dt format ICT-2249 Global search location filter - Province not prepopulated on stage issue | ICT-2306 fixed issue ICT-2378 fixed issue, add logic for date format and energy performance format ICT-1724 the block ticket for datahub test QA - Testing | work stage port issue analyze work on ICT-2445(#2,#3 need Mike create new ticket to check in code) | test: https://gryphtech.atlassian.net/browse/ICT-1363https://gryphtech.atlassian.net/browse/ICT-916https://gryphtech.atlassian.net/browse/ICT-1361https://gryphtech.atlassian.net/browse/ICT-1362https://gryphtech.atlassian.net/browse/ICT-938 | DH code fixing issue chen is aware, of missing code from dec-14 branch - fixing bug |  |  |  | 1hour to prepare review 2hours review meeting ICT-2453 fix issue ICT-2454 |  |  | 929- datahub x-fer agent - discovered root cause for email send issue |  |  | ICT-2372 Representing agent change for Brasil (Important - Hotfix) ICT-1783 Remax Poland Wants to See the Currency Symbol After the Amount ICT-2470 | ICT-2187 Regression - Global referral - RA user - Status buttons ICT-2190 Regression - Global referral - RA user - Edit icon should not be visible ICT-542 Switzerland CRs - Selected all contacts count is incorrect based on lead source category ICT-2251 Regression - Region admin unable to edit Buyer match | ICT-2390 iList API - New endpoint and Integrator ID Proptexx | ICT-2390 iList API - New endpoint and Integrator ID Proptexx | ICT-2339 Done ICT-2475 - |  |  | ICT-227 |  |  | Datahub/testing | ICT-2027 test and fix bug |  |  | (ICT-2027,ICT-2030 ) implement the separate the listing and selling end | ICT-1724 ICT-2258 ICT-2489 | ICT-2473 ICT-2514 ICT-2027 | ICT-2343 GTM Tracking | ICT-2027 discussed with pankaj, rollback ilist7 SP, created new SP for ilist10, and updated ilist10 code |  |  | ICT-1985 analyzing | ICT-2500 Change Intl Sales Associate ID to Enterprise ID | ICT-2500 Change Intl Sales Associate ID to Enterprise ID ICT-2515 Updates to Office Staff Profile |  | Office/profile stuff, ilist7 impersonate agent issue |  |  | ICT-2541 Regional tools integration - RE/MAX title issue ICT-2512 UAT - Country list for GR and GS | ICT-2512 UAT - Country list for GR and GS | ICT-2541 Done ICT-2560 Regional tools - Missing “Action request” email from iList10 when change title from Associate to Owner/manager | ICT-2027 new spec from pankaj discussed with QA | ICT-2027 - comparing DH and ilist10 - requires discussion |  |  | ICT-2587 Regional reporting - Transmittal report - displayed as Listing end count-1 when User selects Both side transaction ICT-2558 UAT - Lookups - Mapping - the current mapping are incorrect in Client Motivation |  |  | ICT-2576 |  |  |  | ICT-2562 Global Search - Criteria are not remembered while hitting back browser button ICT-2638 Regional tools integration - Transfer agent/office admin - missing Terminated reason and RE/MAX title under Datahub info | ICT-2651 Regional reporting - Transmittal report button Logic - see error after clicks on Transmittal report button ICT-2647 Can NOT create new transaction for RE/MAX listings ICT-2404 LAR - Subject | ICT-2403 LAR Report Screen ICT-2404 LAR - Subject ICT-2405 LAR - Title, Address & Photos ICT-2656 UAT - BM map search not working ICT-2649 UAT - JS errors - Add Property from Edit Contact page | ICT-2677 CR - 147696 - RX Brasil - ImovelWeb -Add Super Highlighted option - Listing adv tab for ImovelWeb ICT-2678 CR - 147795 RX Brasil - PadraoiList, FormatoPadraoGroupoOLX- Implement highlights options as similar to GroupoOLX and include the same in feeds ICT-2649 UAT - JS errors - Add Property from Edit Contact page | ICT-2611 Global Referral - Card displayed on iConnect landing page for iList user ICT-2692 UAT - Floor plan upload error - PDF only |  |  | ICT-101 Potential Buyers Notification email issues - dev see comments |  |  | ICT-2511 Step 1 - Copy macro office data from REMAX DB to REP2 DB ICT-2594 Transmittal report changes
[7 empty] | Graham - 2029,2027 - Blocked |  |  | Mike ict-2216 gets room type = good, "get feature" = Error received |  |  |  | Blocker: Riya tested exclude agent from the website yesterday, this was not showing on website, we need Robin helps | [27 empty] | datahub - meeting on monday?, mike's suggesting not working | [12 empty] | ICT-929 need discuss and work on it (x-fer agent with DH/ifranchise) | [6 empty] | working on dated, Dec-14 branch - ?? add migration scripts or update branch? | [11 empty] | DH: billing mo/yr calculations - DH needs to post transations for latest months | [30 empty] | Meeting with Proptexx Monday morning - incomplete work - then we determine proptexx work
| Dev |  |  | Dec 23 - Create Global Referral Bug | ICT 2164 - Done, ICT 2251 Assigned to mike | ICT 1784 - Regional Reporting - Related Income Grids > UI Updates | ICT 2255 - Updating Label ICT 2250 - Global Referral Validation |  |  | ICT 2250 - Assigned to Product, ICT 1784 - Assigned to design |  |  | ICT 1988, ICT 2021 | ICT 252 - Office Maintenance |  |  | ICT 2270 - creating new property in hebrew |  |  | ICT 1874 - transaction tab/reporting -design needed to shorten height, ICT 2270 | ICT 2297 - Contact issue- not able to edit contact details |  |  | ICT 2109 - Foreign Properties ICT 2105 - On sale - Main Setting |  |  | ICT 2188 - Add Referral bug ICT 2112 - Investment Properties Regional Setting | ICT 2298 - Global Referral ICT 2122 - Investment Properties |  |  |  | ICT 563 - Feedback - Agent Profile - Quality Meter missing, ICT 2230 - UAT - Cannot Create Contact, ICT 2331 - Inline Translation Failure | ICT 2335 - Transfer Agent Bug ICT 125 - Lead pipeline | ICT 2298 - Global Referral Side menu changes ICT 2319 - New Referral - wrong pop-up for comment | ICT 2349 - Preferred Language is not saved ICT 2348 - UAT - Contact Update does not preserve in other language |  |  | ICT 2349 - Preferred Language is not saved |  |  | ICT 2348 - UAT - Contact Update ICT 836 - Add Linked in button | ICT 2297 - Contact issue- not able to edit contact details ICT 542 - Selected all contacts count is incorrect based on lead source category |  |  | ICT 542 - Selected all contacts count is incorrect based on lead source category [ICT-2389] Urgent! e-Signature Data Request - Jira (atlassian.net) | ICT 2426 ICT 2282 ICT 2434 | QA - Testing Bug - Impersonating a belgium region admin issue | ICT 2304 - Staging - Persistent Warnings & Errors (3) | Belgium impersonation issue ICT 2304 - Staging - Persistent Warnings |  |  |  |  | ICT 2307 - iList 10 - Expose all regional setting in iLIst 10 UI for Tenant admin role ICT 2446 - iList 10 - Expose all regional setting in iLIst 10 UI for Tenant admin role | ICT 2300 - Global Referral: Changes to "My Network" page ICT 2377 - UAT - Missing translation - Emails to you ICT 2459 - Important!!! Badges for Mobile app download Update - Hotfix | ICT 2249 - Stabilization - Global search location filter - Province not prepopulated to agent province selected on office profile |  |  | ICT 2427 - UAT - Listing address saved in hebrew displays in english ICT 125 - Agent Performance Page - Leads pipeline box UI issue in RTL | ICT 2084 - Global Referral - Updates to No Response for X Days Email Rules | ICT 2349 - Contact Details - Preferred Language is not saved anymore | ICT 2191 - Regression - Global referral - RA user - Error while save/send a comment ICT 2468 - Regression - Global Referral - History Section - On behalf of user themself | ICT 563 - Feedback - Agent Profile - Quality Meter missing |  |  | ICT 2434 - Stabilization - Transfer Tools - Transfer Agent - Region drop down is not displayed for Region admin with access to multiple regions ICT 2481 - Regression - Global referral - RA user - view profile button is directing to RA profile page |  |  | OOO |  |  |  | ICT 4 - Contact Export issues ICT 2427 - UAT - Listing address saved in hebrew displays in english | ICT 2427 - UAT - Listing address saved in hebrew displays in english | ICT 2482 - UAT - Original listing date and expiry date change on save |  | ICT 2134 - Global referral - first email to non-iList agent - google translate is showing truncated |  |  | ICT 1526 - Estimate: Global Search Enhancements ICT 2377 - UAT - Missing translation - Emails to you |  |  | ICT 2473 - UAT - Lists - Include/Exclude and reorder not working ICT 4 - Contact Export issues | ICT 2522 - UAT - Buyer match results - pagination not working ICT 2134 - Global referral - first email to non-iList agent - google translate is showing truncated |  |  | ICT 1513 - Global Search - Price Type, Expiry Date, Energy Efficiency values are incorrect | ICT 2397 - Agenda- Event appear gets disappear sometimes ICT 2487 - UAT - "Add Referral Request" On the Agent Dashboard Doesn't Work | ICT 2561 - Stabilization- Changes made to existing properties is not updating | ICT 2569 - Stabilization - Agenda - time is not updating when dragging all day event to hour's event ICT 2573 - Regional Tools Integration - able to enter 15 characters in 'Enterprise Office ID' field | ICT 2559 - Property Detail Page- Can't update Energy efficiency as Not Selected | [12 empty] | ICT 2655 - UAT - Agenda cannot be added in the past 2 ICT 2658 - Listing details - Listing Title/STR# - Validation messages | ICT 2686 - BM - Search for Buyers - Bedrooms is mandatory for performing a search ICT 2649 - UAT - JS errors - Add Property from Edit Contact page ICT 577 - Agenda - Task list - Priority filter is preserved incorrectly |  |  | ICT 2683 - BM - Search for Buyers - Location search
|  |  |  | ICT 1264 - Contact address bug , ICT 2251 - Region Admin Buyer Match | ICT 1784 - Regional Reporting - Related Income Grids > UI Updates |  | ICT 2250 - Global Referral Validation |  |  | ICT 1874 - Regional Reporting |  |  | ICT 252 - Office Dropdown issue |  |  |  | ICT 2289 - Contact- Automatic country value doesn't restore issue | OOO | ICT 1874 - Regional Reporting - Related Income grids - UI Updates | ICT 2297 - Contact issue- not able to edit contact details | ICT 2109 - Foreign Properties |  |  | ICT 2108 - On sale - Turn on for regions script |  |  | ICT 2298 - Global Referral: Side Menu Changes | OOO |  |  | ICT 563 - Feedback - Agent Profile - Quality Meter missing | ICT 508 - Region pull down based on setting | ICT 2295 - UAT - Error when viewing a referral | ICT 2349 - Preferred Language is not saved | ICT 125 - Agent Performance Page - Leads pipeline box UI issue in RTL |  |  | ICT 2373 - Transfer tool - Transfer Agent - translations are not working ICT 2374 - Transfer tool - Transfer Agent - Validation messages are not displayed |  |  | ICT 2297 - Contact issue- not able to edit contact details | [ICT-2389] Urgent! e-Signature Data Request - Jira (atlassian.net) |  |  | ICT 2426 - Stabilization-Transfer tool - Transfer Agent - Not able to save after selecting all the mandatory fields ICT 2373 - Transfer tool - Transfer Agent - translations are not working | QA - Testing | ICT 2304 - Staging - Persistent Warnings & Errors (3) ICT 2307 - iList 10 - Expose all regional setting in iLIst 10 UI for Tenant admin role | [7 empty] | ICT 2249 - Stabilization - Global search location filter - Province not prepopulated to agent province selected on office profile | ICT 2427 - UAT - Listing address saved in hebrew displays in english |  |  | ICT 2084 - Global Referral - Updates to No Response for X Days Email Rules | ICT 2349 - Contact Details - Preferred Language is not saved anymore | ICT 2191 - Regression - Global referral - RA user - Error while save/send a comment | ICT 563 - Feedback - Agent Profile - Quality Meter missing | ICT 2434 - Stabilization - Transfer Tools - Transfer Agent - Region drop down is not displayed for Region admin with access to multiple regions | [6 empty] | ICT 2427 - UAT - Listing address saved in hebrew displays in english |  |  |  | ICT 2479 - UAT - Cannot add property in RTL - hotfix ICT 2482 - UAT - Original listing date and expiry date change on save |  |  | ICT 1526 - Estimate: Global Search Enhancements ICT 2377 - UAT - Missing translation - Emails to you | [5 empty] | ICT 2522 - UAT - Buyer match results - pagination not working ICT 2134 - Global referral - first email to non-iList agent - google translate is showing truncated | ICT 2521 - UAT - CMA no geo data for RA and null file |  |  | ICT 2397 - Agenda- Event appear gets disappear sometimes | ICT 2084 - Global Referral - Updates to No Response for X Days Email Rules | ICT 2559 | ICT 2559 - Property Detail Page- Can't update Energy efficiency as Not Selected | [10 empty] | OOO | OOO | ICT 2655 - UAT - Agenda cannot be added in the past 2 |  | Needs work
[42 empty] | Need to talk to QA about ICT 542 ( scheduled for after standup) | [58 empty] | ICT-2575 - no epic, has changeset, in Todo
| Architect | [8 empty] | Met with frank |  |  |  | Finished data load marketing editor task |  |  |  | data load changes, merged back changes for Dami + UI for layout editor |  |  | permissions findings - R & D Rob's tickets - load balancing ilist7 Dami's branch Load times - implemented Frank's fix Pre integration branch into Stage with Gaurav | [11 empty] | Resolving baseless merge conflicts from "Dami's branch" - approx 200 remaining conflicts | [11 empty] | Christophe issues completed | [42 empty] | Agent Profile - done | profile performance - fixes headlock fixes - reduced transactions/concept | Performance related tickets checked in | [14 empty] | Marketing on Demand - copy template
|  |  |  | Performance procs for latency - mobile Meeting with Aleem? | Marketing editor - will divide and conquer with Frank |  |  |  |  | ICT-2247 - backend data load |  |  |  | Need to meet with Frank |  |  |  | Rob: assigned misc tickets | ME - impersonation permissions bug | Post-merge to Dami's branch work - merge franks changeset to Dami's | Remaining after discussion end of scrum: - emai logic/rendering with new templates (konva + json logic) - Preview 1) email 2) template Justin working on #2 today and graham to schedule meeting for Monday | [11 empty] | 2nd baseless merge back to integration, again requiring regression |  |  |  |  | Upload of static issue (REP & canva) After justin's research frank can load the MoD editor |  |  |  | Looking at Marketing Editor Code reviews, can assist Christophe - |  |  | Script to create - insert moving fro stage to production | ? ICT-2393 - merge updates required for db storage ? ICT-2429 - template export/import b/w env. | ME - ICT-2438 ME- ICT-2439 - delete stored proc me-ICT-2429- copy template b/w environments ICT-2299 - super admin permissions | [13 empty] | ICT-2478 - ME editor final | deprecating azure function for html to pdf - not using it. PHX function is called - investigating | [10 empty] | Rob: esignature project - documentation review, demo for generic best practices, development and sp creation | demo for technology meeting this afternoon. sp's and optimization | ICT-2162 profile performance |  | head lock issue and performance | [9 empty] | ICT-2517 - Head Locking issue ICT-2291 - resolve 1) logging (for future incidents), 2) Load balancer issues ICT-2162 - Agent Profile performance ICT-2261 - Delete non-ilist users | Head locking - in progress - needs db monitoring Profile performance - more work | https://gryphtech.atlassian.net/browse/ICT-2564 - created Copy Create Template Function - From REP to iList10 | Copy/Create Rep to iLIst10 | [10 empty] | highest priority - 'audit trail - not functioning - WEB-1039 Image render Layout Editor - Work with Frank |  | Create new template merge from REP to ilist10 | Features needed built that changes rendering OTF. Scope increased slighty with anticipation of necessity. Checking code in today | Audit Trail function REP-1931 - PDF UI issues
[10 empty] | Need meeting to finalize flow - Graham | [22 empty] | Might need to regression test branch | [56 empty] | historical ME changesets in REP must also be applied to iList
Mobile Dev
| Website Dev | [5 empty] | yesterday: a. iRender -- Stage Porting Folder DONE -- Support Ticket CR#147161 b. REP -- Agent Profile Migration from KW4 to KW6 & KW2 | [6 empty] | yesterday: REP website refresh - Team Profile - DONE
[6 empty] | REP WebSite Refresh - Agent Profile | Today: a. REP -- Agent Profile Migration from KW4 to KW2, 3 & 5 | [6 empty] | today: a. REP website refresh - Office Profile b. iConnect assisstant | [45 empty] | Area Guides: Robin needs to be connected with IC team - future changes - IC & iRender 1) dev branch 2) merge, port, & testing process Merge - order of operations (e.b. build locally, copy .dll's)
[21 empty] | ICT-2180? - talk to nitish a/b dependency agent in training - Graham | [33 empty] | https://gryphtech.atlassian.net/browse/WEB-1039
QA | QA Lead | [68 empty] | Reviwed flow for DH tests, Chen is now testing
[5 empty] | assistance with port and test | few user stories left for the sprint, will continue validation after non ilist user script runs successfully. | [6 empty] | STage port verification and ramping of new members |  |  |  |  | Team is working on tickets - sent over to test, then final review for stage | [23 empty] | ICT-1744 - needed pankaj assistance? (new user in ilist7/10 not showing on DH) ict-542 - discussed - what's left to be discussed? - Sheetal, now with Azeem - done, must demo |  |  | Log ME Bugs in this spreadsheet for prioritization: |  | Marketing Editor - https://gryphtech.atlassian.net/browse/ICT-2268 - used closed or "ready for..." tickets NOTE: This project is atypical Layout editor bugs - Dami's work https://gryphtech.atlassian.net/browse/ICT-2268 | [12 empty] | Please see that ICT-2378 - and mobile app stage for ilistquestion |  | few tickets in stage verification? (global referral ticket 542, Regional Settings Ph.2 in anticipation of ME | test tickets |  |  | tasks and user stories, uat ticket on test - all tickets outside of regional tools |  |  | Datahub/sync - provide cases, review transaction report When tickets are ready, they will port to stage DH & Proptex = priority |  |  |  |  | Test work - last one related to GR log - need dev teams suppot Final regression on stage | VAlidated tickets on test, production port | 5 tickets on test, one resource, | [6 empty] | Waiting on DH to finish QA work for release 10.17 next week | DH refreshed DB (reporting period) - uncertain if finished Must create data on our side (agent/transactions) |  |  | 10.17 tickets |  |  |  | Clear board tickets by priority |  |  | Finishing up DH Porting sanity check |  |  | Test/ Release
[10 empty] | No user stories to test in current sprint board for Regional Tool - production - environment has issue - no tickets ready for QA | [9 empty] | Datahub region tickets - Datahub must grant permission (was working before and stopped) - Mike to reach out to client - all (27) tickets moved from spriont to sprint - no movement - ICT-913 cannot be worked on - roadblock!! | [41 empty] | Parallel QA between ilist7 & 10? | [13 empty] | Go ADO/JIRA integration | [11 empty] | Carlos Emails - UAT - Reconcile w/ knowledge of existing work handling? 10.16: all closed, not ICT-1362 or ICT-928 | [16 empty] | Needs acceptance criteria for Proptexx criteria
| QA | [8 empty] | Dedicated resource for global referral |  |  |  | (10) stage tickets |  |  | stage tickets - completed! |  |  | test environment tickets & produciton release regression | Test environment | [9 empty] | tickets on test/stage | tickets on test/stage |  |  | tickets on test regression testing on productoin last night |  |  | Tested user stories, finished bugs on test |  |  | tickets on stage, continued testing |  |  |  | focused on Stage |  |  |  | cleaning up regional tools | [5 empty] | Regression testing on Global, ilist10/ilist7 on Stage | focused on GR regression test and submitted bugs |  |  | completed Test tasks |  | cleaned stage - ready to go! |  |  |  |  | 1) datahub - tickets in QA - all related to transactions, office profile is on stage, transactions are on test |  |  |  | Test & Stage | [18 empty] | agents and offices mapped (DH) | production | [12 empty] | Stage - regression/testing finished, | TEST tickets STage tickets | finishing up QA test, stage tickets, then test case build |  |  | Remaining test tickets, test case for LAR, and stage - after port
[14 empty] | working on remaining stage tickets |  |  |  |  | Production port smoke test & regression | Test environment - | Create new users and continue with Test | [9 empty] | continue work on test | continue work on test | [8 empty] | 1724 added to sprint |  |  |  | today also stage, found issues and sent back - |  |  |  | 918, 919 - not getting integration bugs (missing coded - chen is aware, of missing code from dec-14 branch) | [6 empty] | TEST tickets today |  |  | Stage today after Friday port | stage focus for release tomorrow. | [5 empty] | Need assistance with the Regional Tools testing: - prepare tools 3 months billing month and year data: identify offices, identify test data, data, transacitons, & agent lists scenerios, set billing month - must have same database, same connection, - API used to call DH - same agent list - pushing data into ifranchise (we did not work on ifranchise integraiton, but we use the logic integration to pull into list10 e.g. "YTDs" - after transmittal we sync data |  |  |  | contentrating on Test tickets today |  |  | Cleaned up test issues. 10.16 release ready for stage |  |  |  | Test environment, after stage port, regression and test | [6 empty] | DH & 10.17 |  |  |  |  | should be able to start testing transactions today | Test/ dev tickets | [10 empty] | STage tickets |  | Production smoke test
[20 empty] | Graham to reach out ot Gaurav | [11 empty] | Unable to edit users | [26 empty] | Office profile is available? checked settings, if no data, is not integrated (Stage) - maybe create a new office to test (only one env available | [6 empty] | DEV: Global referral & UAT Regional Settings, Transfer Tool
| QA | [32 empty] | kj
|  |  |  | cleaning up board tickets and answering Azeem questions | [29 empty] | lkj
lkj