## Slide 1: One Content Workflow
Start Date | March 2019
Original Program Manager

## Slide 2: Graham Cohen One Content Workflow (Year in Review)
Labeler - Job Post Migration
Job Post vendor management workflows are migrating to Labeler due to deprecating TTurkey platform. Integration with Salesforce
Logic Gates: Lead Quarantine, Recycling & Re-engagement (in definition phase)
Stand-alone platform to surface and prioritize previously seen company leads to callers in Salesforce, based on business rules & quarantine durations
Salesforce - Lead Management
Salesforce build of current, manual operations in Sheets. Migrate all Content Acquisition users from AdCentral CRM to Salesforce CRM
End-to-end integration & automation of projects:
Competitor Tracking & Deep Thought
Data collection from competitor websites, globally. The cleaning & normalization & v2 AdCentral matching with internal data stores
Labeler - SCOUT Migration
SCOUT vendor management workflows are migrating to Labeler due to deprecating TTurkey platform. Integration with Deep Thought & AdCentral/Salesforce
NOTE - On October 9th, the team split and transitioned. Content Operations (COPS) is now with Lead Gen and Content Acquisition (C.A.) is within Sales

## Slide 3: ONE CONTENT WORKFLOW - High-level Timeline
November | December | January | February
14 | 24 | 2 | 9 | 12 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 10 | 16 | 24 | 28
Salesforce MVP Build - Timeline - Q1 delivery for staggered rollout by market & featureset
Labeler Build - SCOUT
TBA Build and COPS QA Test of Tturkey workflow migration
SFDC Pilot Kickoff
SFDC Pilot Close
Labeler - SCOUT - User Acceptance complete
SFDC MVP Wave 1 Release
Salesforce Pilot (AU) - Feedback collection during MVP build process. Manual, Bulk lead upload - no more Rep Sheets for lead delivery
SFDC MVP Wave 2 Release
Labeler Build - Job Post - Migration of Job Post workflows into Labeler - TBA development
Labeler SCOUT - Training & Field readiness
Labeler - Full Deployment
Labeler Scope - Job Post - requirements, scope & estimates
Labeler Build v2 - Job Post - SFDC Integration
Deep Thought - AdCentral Matching v2 - Timeline - Machine learning - (IT), (ES), (BR), (JP) & (SG)
AdC Matching - Complete (IT), (ES), (BR), (JP) & (SG)
Deep Thought - AdCentral Matching v2 - Timeline - (NL), (PL) & (SE) - QA ONLY
)
Havarti Deprecation (dependency)
**Not included: Logic Gates Project - Definition Phase