## PBGO ROADMAP
PROJECT ROADMAP
| APRIL | [11 empty] | MAY | [30 empty] | JUNE
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
MILESTONES
Test
Develop
Launch
General Testing
Sprint 5
Sprint 6
ADDITIONAL BUGS
GO LIVE
BETA
BUG FIXES ROUND 1
BUG FIXES ROUND 2
Sprint 5 W1 Release
Sprint 4 W2 Release
Sprint 5 W2 Release
Sprint 6 W1-2 Release
Beta Release
Final Release
Regression
Acceptance
Sprint 4

## SPRINT DETAILS
| SPRINT 4 | SPRINT 5 | SPRINT 5 | SPRINT 6
| W2 | W1 | W2 | W1-2
RELEASE DATE | 2021-04-20 | 2021-04-26 | 2021-05-03 | 2021-05-17
| TASKS AND MSSGS | CONTAC DETAIL | - Ancillary Screens - Tag Contacts, Add Notes, Subscribe to saved search, other? | CALENDAR
| TASK LIST | CONTACT FILTERS |  | DASHBOARD
| TASK DETAIL | CONTAC LISTING |  | NOTIFICATIONS
| TASK CREATE | CONTACT SEARCH
| TASK EDIT | LISTINGS
| TASK FILTER | LISTING DETAIL
| BUG FIXES | LISTING SEARCH
LISTING FILTERS
|  | MESSAGES LIST EMAILS | GESTURES
MESSAGES LIST TEXT
EMAIL DETAIL
SMS DETAIL
SEND EMAIL
SEND TEXT
BUG FIXES