## Graham -Resume & Profile
Resume, Storage, Attribution, Profile, Update/Sync Clickstream inclusion
Action? | Requirements | Milestone | Additional | Status
| Establish Overall Volume | Planning |  | Complete
| Resume receipt (or normalized meta attributes) | Planning |  | In Progress
| Rules for Account Merge - | Planning | Content Freshness, LIFO? | In Progress
Ashwin to define the data | Determine ALL Indeed tools using Job Retrieval API | Planning |  | In Progress
| Project Plan | Planning | NOT Shared Doc | In Progress
| Questions Doc | Planning | Questions sent to GD Team | In Progress
Ashwin to speak with legal - action item (other than Resume Search) Graham to follow up on legal tickets and purpose - and additional use cases follow up with Ashwin | Resume Usage - Indeed Teams | Legal | Which teams can use resume?
Alex & Bill & Ashwin to discuss acceptable latency & availability - thresholds | ProfIO Latency for Usage | Planning | Availability & latency thresholds to meet |  | PROFPLAT | DEV
[5 empty] | GD | Prod
full text of resume - GD must need a service 1) indeed to build data shape 2) GD to build service 3) refreshed F | Resume Service - (GD side) | US MVP Search Results | Indeed to consume resume through Job Retrieval API for "high availbility" & "low latency" - from Sovren? Job Retrieval Service requires: - Glassdoor accountid - Full Text of profile
full text or extracting meta: | Modeling extrapolation | US MVP Search Results | Myindeed: Resume pro & post processing logic for meta data - Question whether ProfIO will be storing meta (from MDS) or resume
if service available for data, is addl. data available? Indeed not to use data, but might be "interesting" | Additional Data (with Resume) | US MVP Search Results | Comparisons for product purposes - what additional data?
Solution TBD - 1) new db 2) flag as "Private" - existing field, - ALSO another field called "searchable" (some teams key off searchable (biz logic introduced in search) vs private) - SEE RESUME USAGE ABOVE - Need to know how resumes are flagged in DB | Resume Attribution | US MVP Search Results | GD Resume cannot be shown to employers "private" flagging required
| Resume Sync - Periodic | US MVP Search Results | (GD has internal process for moderation, could potentially be used for resume refresh) Indeed sees 150k-350k rez updates per day, which is roughly 0.1-0.3% of total documents. Of course, users who update their resume seem to be more active in search, which makes sense given that they're already on the site
remove niffler for CTK and extend to profile - Profile has data drop mechanism - existing | GDPR Sanitization | US MVP Search Results | JRS API - Sanitation Request nearly complete
Graham to ensure is being taken care of by ranking team | Unification of CTK | US MVP Search Results | CTK "Change Tracking" files contain list of changes since VM was last backed up - on all machines where "change block tracking" is enabled
Graham TO ENSURE IS OUT OF SCOPE | Account Creation for Consumed Resume | Post MVP
Graham TO ENSURE IS OUT OF SCOPE | Account merge/Dedupe | Post MVP | Common email address - Existing accounts
OUT OF SCOPE | Two-way data sync - with Personalization Service | Post MVP | Niffler Data
resumes from GD by Q3, JRS built by Q2, build JIRA (post MVP for Job search, but is Profile MVP) | Resumes be made available to Job Retrieval Service (JRS) API | Post MVP | JRS API
Ashwin to follow up with Graham later on | JobService/RezService Integration | Post MVP | SQRANKING-408 - make a request to rezService from JobService with an accountid that we receive in the GD JRS request and the response from RezService needs to be consistent with what we're currently getting for Indeed Resumes
Post MVP
There is an opportunity on Profile side, but this is most likely for employer. Might not be an opp at all - what is use case of what will be unlocked with OAuth | Oauth with GD | Post MVP | "enhanced profile" on GD using Dradis info will now require Oauth
Backlog (Emma built this) - goal of co-reg is to create a profile on Indeed that user can log into, not the same as oauth | Co-registration: Indeed & Glassdoor | Post MVP | Enables one-way data sharing Simple effort to implement Email all Glassdoor users to share Glassdoor profile with Indeed (to collect opt-in)
Other
owned by RR | A/B Testing?
has not come up in convo | Taxonomy & Attribute Returned to GD In Service
DAvid Tulig - Needs more investigation - far after MVP | Click to Apply from GD (Apply with GD Resume on Indeed)
N/A | Cross-site advertising |  | based on resume/profile

## Resources & Agenda
Docs "Ranking" | Meeting with Profile |  |  | Contacts
Integration Ideas (early) | Meetings | Please include |  | Brianna Jiang - Product - briannAshwinjang@glassdoor.com
| Review list items - pipeline exists? | Run through this list for validity and/or missing items |  | Tony Hawke - Engineering tony.hawke@glassdoor.com
1-Pager - Profile/Resume | Prioritize together on Josh_Ashwin tab | Once we have a good list, we can copy into another Sheet or rank and re-order here
Lucidchart Flow | Alignment with OKRs? | is with OKR
SQRANKING | JIRAs, Stories, sizing? | JIRA example - Milestone (Epics) - Graham to enter from this list? Grouping for milestones | JSAPI - JIRA - MIlestone 1
UIL Gantt | ProfIO storage (pre/post MVP)
account linking proposal | Risks & Blockers | need to close on open quesitons - TBD with discussion of GD timeslines
Job Search - Use Cases | Out of scope
Metadata & Tax 2020 OKRS
JSAPI - JIRA - MIlestone 1
GD Feature Phasing - Approach by feature
Profile Shared
Profile NOT Shared
Job Search - Use Cases
UIL - Pipeline
Data flows (for legal)
Niffler integration design review
Ranking Milestones

## JIRA Ticket Creation
REQ-138011 |  |  |  | Resume, Storage, Attribution, Profile, Update/Sync Clickstream inclusion
Subject | Action? | Description | JIRA | Requirements | Milestone | Status
Profile ¦ GD Integration - Determine ALL Indeed tools using Job Retrieval API | Ashwin to define the data |  | https://bugs.indeed.com/browse/GD-24 | Determine ALL Indeed tools using Job Retrieval API | US MVP Search Results | In Progress
Profile ¦ GD Integration - Questions Doc |  | Questions sent to GD Team | https://bugs.indeed.com/browse/GD-25 | Questions Doc | US MVP Search Results | In Progress
Profile ¦ GD Integration - Resume Usage - Indeed Teams | Ashwin to speak with legal - action item (other than Resume Search) Graham to follow up on legal tickets and purpose - and additional use cases follow up with Ashwin | The existing request was focused on the core job search use case. I deliberately left resumes out for a separate review since we weren't sure yet how that was going to work. Do you think we're in a good enough state yet to start that conversation with Legal? | https://bugs.indeed.com/browse/GD-26 | Resume Usage - Indeed Teams | Legal
Profile ¦ GD Integration - ProfIO Latency for Usage | Alex & Bill & Ashwin to discuss acceptable latency & availability - thresholds | Availability & latency thresholds to meet | https://bugs.indeed.com/browse/GD-27 | ProfIO Latency for Usage | Planning |  | PROFPLAT | DEV
[7 empty] | GD | Prod
Profile ¦ GD Integration - Resume Service - (GD side) | full text of resume - GD must need a service 1) indeed to build data shape 2) GD to build service 3) refreshed F | Indeed to consume resume through Job Retrieval API for "high availbility" & "low latency" - from Sovren? Job Retrieval Service requires: - Glassdoor accountid - Full Text of profile | https://bugs.indeed.com/browse/GD-28 | Resume Service - (GD side) | US MVP Search Results
Profile ¦ GD Integration - Modeling extrapolation | full text or extracting meta: | Myindeed: Resume pro & post processing logic for meta data - Question whether ProfIO will be storing meta (from MDS) or resume | https://bugs.indeed.com/browse/GD-29 | Modeling extrapolation | US MVP Search Results
Profile ¦ GD Integration - Additional Data (with Resume) | if service available for data, is addl. data available? Indeed not to use data, but might be "interesting" | Comparisons for product purposes - what additional data? | https://bugs.indeed.com/browse/GD-30 | Additional Data (with Resume) | US MVP Search Results
Profile ¦ GD Integration - Resume Attribution - Private vs searchable | Solution TBD - 1) new db 2) flag as "Private" - existing field, - ALSO another field called "searchable" (some teams key off searchable (biz logic introduced in search) vs private) - SEE RESUME USAGE ABOVE (GD-26)- Need to know how resumes are flagged in DB | GD Resume cannot be shown to employers "private" flagging required | https://bugs.indeed.com/browse/GD-31 | Resume Attribution - Private vs searchable | US MVP Search Results
Profile ¦ GD Integration - Resume Sync - Periodic |  | (GD has internal process for moderation, could potentially be used for resume refresh) Indeed sees 150k-350k rez updates per day, which is roughly 0.1-0.3% of total documents. Of course, users who update their resume seem to be more active in search, which makes sense given that they're already on the site | Frequency/refresh question asked in GD-28 | Resume Sync - Periodic | US MVP Search Results
Profile ¦ GD Integration - GDPR Sanitization | remove niffler for CTK and extend to profile - Profile has data drop mechanism - existing | JRS API - Sanitation Request nearly complete | https://bugs.indeed.com/browse/GD-32 | GDPR Sanitization | US MVP Search Results
Profile ¦ GD Integration - Unification of CTK | Graham to ensure is being taken care of by ranking team | CTK "Change Tracking" files contain list of changes since VM was last backed up - on all machines where "change block tracking" is enabled | https://bugs.indeed.com/browse/GD-33 | Unification of CTK | US MVP Search Results
Profile ¦ GD Integration - Account Creation for Consumed Resume | Graham TO ENSURE IS OUT OF SCOPE |  | Out of scope - TBD | Account Creation for Consumed Resume | Post MVP
Profile ¦ GD Integration - Account merge/Dedupe | Graham TO ENSURE IS OUT OF SCOPE | Common email address - Existing accounts | Out of scope - TBD | Account merge/Dedupe | Post MVP
Profile ¦ GD Integration - Two-way data sync - with Personalization Service | OUT OF SCOPE | Niffler Data | Out of scope - TBD | Two-way data sync - with Personalization Service | Post MVP
Profile ¦ GD Integration - Resumes be made available to Job Retrieval Service (JRS) API | resumes from GD by Q3, JRS built by Q2, build JIRA (post MVP for Job search, but is Profile MVP) | JRS API |  | Resumes be made available to Job Retrieval Service (JRS) API | Post MVP
Profile ¦ GD Integration - JobService/RezService Integration | Ashwin to follow up with Graham later on | SQRANKING-408 - make a request to rezService from JobService with an accountid that we receive in the GD JRS request and the response from RezService needs to be consistent with what we're currently getting for Indeed Resumes | https://bugs.indeed.com/browse/GD-22 | JobService/RezService Integration | Post MVP
Post MVP
Profile ¦ GD Integration - Oauth with GD | There is an opportunity on Profile side, but this is most likely for employer. Might not be an opp at all - what is use case of what will be unlocked with OAuth | "enhanced profile" on GD using Dradis info will now require Oauth |  | Oauth with GD | Post MVP
Profile ¦ GD Integration - Co-registration: Indeed & Glassdoor | Backlog (Emma built this) - goal of co-reg is to create a profile on Indeed that user can log into, not the same as oauth | Enables one-way data sharing Simple effort to implement Email all Glassdoor users to share Glassdoor profile with Indeed (to collect opt-in) |  | Co-registration: Indeed & Glassdoor | Post MVP
Profile ¦ GD Integration - A/B Testing? | owned by RR |  |  | A/B Testing?
Profile ¦ GD Integration - Taxonomy & Attribute Returned to GD In Service | has not come up in convo |  |  | Taxonomy & Attribute Returned to GD In Service
Profile ¦ GD Integration - Click to Apply from GD (Apply with GD Resume on Indeed) | DAvid Tulig - Needs more investigation - far after MVP |  |  | Click to Apply from GD (Apply with GD Resume on Indeed)
Profile ¦ GD Integration - Cross-site advertising | N/A | based on resume/profile |  | Cross-site advertising