## RETRO
Retrospective
Sprint 98
LIKED: |  | LACKED:
Marketing editor now has structure and desired outcome. |  | Prior thinking put into use cases - Ideas discussed in meetings, next meeting, minds are changed, by the time it gets to engineering, is started, then plans change (e.g. marketing editor - images) questions are asked/asnwered and direction changes
Saw progress through the holidays - even though many people OOO, there was forward movement |  | Objective - more times than not, these meetings result in discussion of process, and not the meeting content (e.g. tickets) Everyone needs to know what to do and when/how to do it (e.g. meeting estimates - developers need to be in front of machines)
Liked the individual task to analyze current code and estimate the larger more complex tasks - sometimes it takes more than grooming session with many other items in consideration. |  | Actual process for estimation
Before when there was an estimate desired, each would research and come back with estimates. There was time to perform the work. Then during estimates session, all were knowledgable and compared each of their estimates for final
Time to analyze the code is lacking (e.g. Proptexx) - especially for complicated things, must be able to dig through the code (e.g. transaction reporting) - consideration of all the dependencies that affect the outcome
Staying within confines of estimates. Perhaps 3 of 4 tasks that take 4 hours, 3 tasks take 1 hour and the remaining tasks... "we start with Google" and the solution is not so easily discovered - then over estimated time
estimates - we have tickets in sprints without estimates. Sets the team up for failure. Tickets without estimates will be swapped with bugs.
Results - lots of discussion, no results, rather layers of complexity
LEARNED: |  | LONGED FOR:
Surviving without Pankaj |  | Would like to see T-shirt sizing performed in grooming, for those that requires deeper estimation - create the tasks for estimation.
Where to source information... without Pankaj |  | When the task is "analyzed" the sr. dev can architect the solution for anyone else to develop (some tasks require more logic than others, that may or may not be transferrable between persons) Can convey code, but not necessary knowledge of details (experience, dependencies, tribal knowledge)
Backlog grooming meeting - spending the time to sit down and go through backlog to fix the things - stop throwing "timebox" solutions at the problem
Entire sprint for "timebox" - clean up the backlog -
Hackathon: Valuable gifts and prizes for whoever closes/fixes most bugs
Sprint 105
≈(3) items business will try to do differently | No Stackify recording - documentation for repeatable process and reference | ≈(3) items team will try to do differently | We should approach one another more often - when there are issues - reach out!
| "Teams: Quiet Hours" - No noise/distractions |  | More smiling throughout the day
| Is a headache to prepare to port-things |  | Source of Truth (PRD vs JIRA Description) RE: Communiction of/when requirements change in meetings, etc. Who is responsible to notify DEV/QA when changes take place? Especially post-DEV/QA-start - Team members do not go back to compare the document and work for accuracy after work is done - the team moves on.
The day when it comes as a product owner where the knowledge exsits and Carlos does not have to be approached
LIKED: |  | LACKED:
Knowledge sharing by the team from iList7 - team was quick to answer | Team work and cross-team communication. Suggestions made and changes performed quickly. QA team works hard. | For price formatting it was estimate for 2 or 2.5 days of work but we didn't take out anything out of the sprint.
All team members and Sheetal were extremely helpful throughout | Team work is great!! Everyone helps each other | We should approach one another more often - when there are issues - reach out!
Team work for QA, Design, Product & Design! Short discussions help with tickets working on - short time to get responses |  | Would like additional time to complete test document - is hurried
I liked team members help each other - Frank and Robin. |  | Sprint is too busy.
Dev undetstand the problems. (perception) compared to the past, things flow much easier now
Sheetal sent a message out of the blue to clarify a ticket - we should do that more often! e.g. must wait until grooming sessions) more effective to get the ball rolling Promotes in-office-like culture
The way everyone helps out cross-team and inner-team (even OOO)
LEARNED: |  | LONGED FOR:
Learned decimals and dollars - handling system wide (looked at a lot of options - eventualy realized had to do things manually) |  | More smiling throughout the day | PRD vs JIRA Description - Requirement changes - who is responsible to notify when changes take place?? (post-dev/QA-start take place -) We do not go back to check the document and work and compare for accuracy after work is done
Learned quite a bit about iList7 |  | Additional planning and analysis with regard to tickets - wants to be challenged with different types and opportunity | Right now developers/QA get 5 minutes to do 1 hour job
Stackify! Very helpful |  | No Stackify recording - documentation for repeatable process and reference
Is a headache to prepare to port-things |  | The day when it comes as a product owner where the knowledge exsits and Carlos does not have to be approached
Learned by asking Frank quite a few questions (specifically iList) this sprint |  | Teams Hours - No noise/distractions
Mike is helping with process - skills required for Product team and development workings |  | Manish estimated 2.5 days of work (decimals & dollars) - we worked on that and excluded the rest of sprint work - we did not remove items from the sprint - need to be cognizant of other, remaining work when these occur
Learns new skills and tests daily - new functions and new platforms |  | We've discussed and planned to have QA estimates performed for sprint
The return of OOO team members!!!!
Sprint 106
≈(3) items business will try to do differently | Clarity at start of sprint for value-items that require focus - not necessarily the "rank", but releases | ≈(3) items team will try to do differently | (iConnect - work on one ticket is multiple systems) more branches so a single ticket can apply to like-changes across all environments (cumbersome: same ticket is for multiple platforms)
| Sprints are overloaded - Add only items we plan on working on int the sprint. |  | Rob mentioned Pankaj is shielding us from aches of porting - What else is lacking? What can we do to make it easier to port - Tell us how we can do more to assist
| Work must be removed from the sprint, if work is added (e.g. 26 items added in sprint #106 after start without estimates) |  | in the following sprint split team into: 1) feature work and 2) carry over items
LIKED: |  | LACKED:
appreciated the extra effort by the team for global referral, including last minute items. |  | more time
togetherness in issues and discussions and team members through discussion |  | Rob mentioned Pankaj is shielding us from aches of porting - What else is lacking? What can we do to make it easier to port - Tell us how we can do more to assist
able to complete tasks once info received from friendly teammates |  | knowledge - when new items are encountered, must ask, stored proceedures, etc (building of tribal knowledge/experience) - doing them isn't necessary to challenging, but info is still required
Worked performed by QA team on iconnect - appreciates the work |  | removing items from the sprint when newly introduced are added
Love working with this team - |  | control of composure and demeanor as a professional in the workplace
LEARNED: |  | LONGED FOR:
Need to ask every step, never assume (e.g. task has multiple items, and must ask for every single feature) - depending who is ask, different response, clarity is diminished |  | Graham to share screen in the morning | sees too many tickets in QA column, can see tickets from older sprints -
learned every day things related to (e.g. global referral) and other product facets |  | strength from within teams for all to get on same page and align | in the following sprint split team for feature work and carry over items
everyday that Agile has many definitions and methods of implementation |  | more branches so a single ticket can include same changes across all environments (cumbersome: same ticket is for multiple platforms)
Longed for consistency and clarity for what to do/accomplish
knowledge of systems
clarity for items that require work - not necessarily the "rank", but releases - only add items we plan on working on int the sprint.
clarity within the items to work on. the "why" - clarity within the items
Items removed, when new items are added, so we are not overlaoding capacity - move to the next sprint because newly prioritized work superceedes these items -
- only add items we plan on working on int the sprint.
Sprint 119
≈(3) items business will try to do differently | Lacked: Time to accomlish the issue. When code is reviewed, it seems as if it was done in haste. Optimization was not there. The investment not made - because of no time - code met equirments only. | ≈(3) items team will try to do differently | Liked: What was proposed, to clean the middle of the board, was highly effective
| Lacked: QA support included as part of estimate (e.g. +30-40%) to encompass back and forth and issue fixing. Estimates should also include QA hours (+ unit test time (test from dev to stage) |  | Lacked: Definitive line for stopping Dev work and starting bug/QA work Lacked: Effective QA process to coordinate between both DEV & QA focus factor
| Longed for: The day when we hear "Good job, guys!" |  | Longed for: QA bugs should be idenitfied days before sprint complete
LIKED: |  | LACKED:
Team is awesome |  | Effective QA process - coordinate between focus factor for DEV and also QA
Really made progress this print |  | Definitive line for stopping dev work and starting bug/QA work
team is going very good - that's why we have a good outcome, sprint after sprint |  | expectations & communication - everyone is working, not a matter of people slacking off, rather expectations needed (and communicated)
Very good job in team, |  | Lacked: Time to accomlish the issue. When code is reviewed, it seems as if it was done in haste. Optimization was not there. The investment not made - because of no time - code met equirments only.
What was proposed, to clean the middle of the board, was highly effective |  | QA support included as part of estimate (e.g. +30-40%) to encompass back and forth and issue fixing - estimates should also include QA hours (+ unit test time (test to stage))
LEARNED: |  | LONGED FOR:
Too much "stick", not enough "carrot" |  | The day when we hear "good job, guys!"
Graham has OCD |  | Closing gaps between product and dev with regard to working on the tickets - longing for focus factor, sprint reflects work needed.
Emails & jobs |  | QA bugs should be idenitfied days before sprint complete
We learn from work every day |  | Expectations cannot be created in real-time after work is done
cleaning up middle of the board, prevented asked for stuff |  | Planning meeting as a prediction of the next spring with regard to prioirty and outcome of next sprint
Organize epics in a way that helps to identify the top feature |  | No bad things.. and also longed for no bad things (e.g. review meeting)
the realization that in a 7 hour day, a 40hr ticket takes 1 week+ to accomlish
If sprint cannot be finished = too much work, inablility to port
Sprint 131
≈(3) items business will try to do differently | Longed for: Test Driven Development: For larger projects - hand-to-hand with QA - near-real time (almost simultaneous involvement) - helps to rapidly identify issues before formally handing off | ≈(3) items team will try to do differently | Learned: If we continue to measure ourselves as a "team", we will be able to align velocity with performance and see great improvment over time
| Longed for: More focus - Spend more time available to focus on the details - if we have more time, the work is more beautful - work is not perfromed well in haste |  | Liked: Azure Devops is very nice (will do more of ADO)
| Learned: Carlos should |  | Liked: Everything is better than before (will do more of everything)
LIKED: |  | LACKED:
Team is good, QA is good! Everyone rocks |  | Time and resources to apply to thesprint.
Allocation - considering everyone involved in the sprint ("team velocity") - and still better than anticipated!
Cleared the board! Looks great!
Everything is better than before
Review meeting was good!
Today's review meeting "right hand to do the right thing"
Azure devops - is very nice
It was a good sprint! Speechless!!
LEARNED: |  | LONGED FOR:
Keep Carlos out of review meetings and retros |  | More focus
If we continue to measure ourselves as a "team", we will be able to align velocity with performance and see great improvment over time |  | Spend more time available to focus on the details - if we have more time, the work is more beautful - work is not perfromed well in haste
In retrospect we should have done this the entire time (team velocity) |  | Test Driven Development: For larger projects - hand-to-hand with QA - near-real time (almost simultaneous involvement) - helps to rapidly identify issues before formally handing off
Sprint 133
≈(3) items business will try to do differently | We are now accepting of the work that we can complete in the sprint. We are able to complete the work - Capacity is aligned with team velocity | ≈(3) items team will try to do differently | Communication: Promises were made. Graham should work harder to discuss with the team to complete the feature work
| More and more natural to work with the different personalities on the dev team - Agile brings us into more contact than Waterfall - communicate all the time now, daily in ceremonies, understand how they think, anticipate learning (e.g. tailor tickets different by dev - example for how we learn how to work with people) |  | Overtasked! Additional time because was unable to accomplish items needed by the team - hopefully soon we'll have dedicated resources to alleviate problem
| Helped with transmittal reports, discovered large Datahub issues and worked through until completion - Good to have found the issue!! - long time project and better to discover sooner than later |  | Exploratory test discoveries (e.g. UX, function) - wish notes were made to go back and correct - submit new issues for
LIKED: |  | LACKED:
Best sprint ever!! Delivered everything that was not blocked - Great Sprint Review! |  | UAT vs Bugs - needs some clarity - how are we going to fit it in (e.g. without estimates, without affecting capacity)
Good sprint review meeting |  | Time!
Sprint was good - 80-90% of the work was completed, had distractions but able to focus and complete (e.g. merge, port - resolve conflicts b/w branches, etc) |  | Communication: Promises were made. Graham should work harder to discuss with the team to complete the feature work
Amount of work completed - felt good! |  | Pending tasks on QA are not able to be completed for whatever reason
Helped with transmittal reports, discovered some issues and worked through until completion - found the issue!! - long time project and better to discover sooner than later |  | Exploratory test discoveries (e.g. UX, function) - wish notes were made to go back and correct - submit new issues for
Team effort - good communication - and thinking to finish everythign
Communicatoin is extremely efficient, when questions come up with devlopers, or developer needs QA to explain, happens immediately for increased speed
LEARNED: |  | LONGED FOR:
Did not learn anything |  | Overtasked! Additional time because was unable to accomplish items needed by the team - hopefully soon we'll have dedicated resources to alleviate problem
Sometimes we have to repeat what is said and learned |  | The solution to an image problem just out of reach
Always learn each sprint, but getting better at what is in the code |  | More time!
Accepting of the work that we can complete in the sprint. We are able to complete the work - Capacity is aligned with team velocity |  | Nothing
Learned a lot about the team
always learns something new each sprint - a good thing!
More and more natural to work with the different personalities on the dev team - Agile brings us into more contact than Waterfall - communicate all the time now, daily in ceremonies, understand how they think, anticipate learning (e.g. tailor tickets different by dev - example for how we learn how to work with people)
Sprint 133
≈(3) items business will try to do differently | Living paycheck to paycheck - (sprint to sprint) - need a build up of estimated backlog. Need an increased amount of time for consideration outside of estimation | ≈(3) items team will try to do differently | Get many tickets upfront, then can easier manage timeline and finish before leaving work for the day
| Features: Some of the user stories are a bit complex, and need to determine missing use cases when developing - need to proactivly raise issues and have the discussion beforehand with QA |  | Estimation has missing parts for the whole of the project - items are not considered for entirety. (perhaps meet with product earlier like in waterfall days to discuss spec and analyze work) More time to considere the many items that require updates - this is missing from the estimation process - missing the breakdown of the work - perhaps need assistance creating a spec to accomlpish this
| Shorter user stories - sometimes they are too big - (e.g. transmittal report time log is around 60hrs) - need to divide up into multiple user stories will lead to greater success and understanding |  | Some tickets - especially for new team members - not descriptive enough and is difficult for those that do not understand the scope of the ticket/function without collaborating with team members
LIKED: |  | LACKED:
Went well! - Not many hiccups (UAT/QA bugs) | The code build is much faster over time - takes 1-2 minutes | Graham not sharing screen
..." " in spite of production issues last thursday/friday | Finished work in time to hand off to QA for test - finished the work in time - moving towards good bandwidth | Estimation has missing parts for the whole of the project - items are not considered for entirety. (perhaps meet with product earlier like in waterfall days to discuss spec and analyze work) More time to considere the many items that require updates - this is missing from the estimation process - missing the breakdown of the work - perhaps need assistance creating a spec to accomlpish this
" " | QA Team finished the sprint tickets - good coordination and communication between teams - went very well! | Living paycheck to paycheck - (sprint to sprint) - need a build up of estimated backlog. Need an increased amount of time for consideration outside of estimation
Most of the tickets made sense | Good experience - everything was done | Description of tickets - it's not self-explanatory sometimes and must collaborate with one another to determine what the actual issue is - the goal write it for the other person to understand the scope of the ticket
Working with QA - determination of whether is on test or dev environement - e.g. transmittal report - good cooperation working together to find problems before goes to prod | developers - quick response to the tickets. Bugs entered were immediately worked | Some tickets - especially for new team members - not descriptive enough and is difficult for those that do not understand the scope of the ticket/function without collaborating with team members
UAT - lots of completed tickets in the right-most column
Sprint board is much more clear than before
Have a good idea to get tickets done
Get many tickets upfront, then can easier manage timeline and finish before leaving work for the day
LEARNED: |  | LONGED FOR:
Canadians are incredible people |  | Features: Some of the user stories are a bit complex, and need to determine missing use cases when developing - need to proactivly raise issues and have the discussion beforehand with QA
Something in between an estimation game and the original "kick off meetings" - ability to look into the code beforehand
Shorter user stories - sometimes they are too big - (e.g. transmittal report time log is around 60hrs) - need to divide up into multiple user stories will lead to greater success and understanding
More time in the office with the team, more fun at work
Sprint
Clear teams capacity - work load in the sprint |  | Some tickets are still missing better acceptance criteria, copying REP logic for REMAX doesn't always work
Good collaboration from Product side
IC SPRINT 137: 04/19 - 05/02
LIKED: |  | LACKED:
lot more clarity on priority of tasks | Dev provided the queries that QA needs for checking DB | Sometimes tickets description or documentation is not updated | requirement doc or JIRA user story tickets better be updated more timely if BA and DEV made agreement on any logic changes
worked as a team including dev/QA/Product to execute sprint to completion | I like all sprints. Ok, the qa work has really seems to have become faster than before. | May be a bit more knowledge on code base before estimating | please don't revert my changes, it hurts
Great team support
Tickets were broken in small tickets, which was good to cover the whole scope | Projects loads faster after rebuild | Dev-QA to talk bwfore US being sent to QA.
Estimated hours are alligning with capacity | BA respond to QA question immediately
worked with prod, can get quick response from prod, make spec clear to move on next step |  | clear spec for understanding by dev/QA
more time to look into code before start working on it
I had a good timebox to get work done, and the entire team was very involved and helpful with conversations
LEARNED: |  | LONGED FOR:
SQL perfomance improvements | I learnd about different functionalities, because i got to work on multiple screens as usual | new QA to be more familiar with rep2 db structure (table...) - training required for database perspective
Datahub or any other projects going down do not interfere with new features
more rep2 table will be used in the function, not only consider remax db | I learned about some rep2 db tables
learned a lot about konvajs and iList10
More in-depth discussions with product when they send requests
IC SPRINT 21: 05/03 - 05/16
Grooming sessions | Groomed way back in the past, team would like to have a refresher
A-Team Concept | Mixed feedback
Collaboration between team members
IC SPRINT 22: 05/17 - 05/30
What should be changed to improve sprint results (1 item from each)
Dev comments on ticket to show the DoD has been met
hire more qa
Demo for major features/Ticket - A team
Peer code review (other than Pankaj)
Finish the features on priority - don’t elongate for too many sprint for lower priority
LIKED: |  | LACKED:
|  | Ticket status and feature availability are not consistent: ticket shows in QA (TEST), but the feature is actually not there in TEST env. | Some features are not well-built or has major blockers, e.g. New Lead box in Team Dashboard is loading forever
For Reports, everytime after fixing some bugs, new bugs emerge
LEARNED: |  | LONGED FOR:
Sprint 106
LIKED: |  | LACKED:
LEARNED: |  | LONGED FOR:
Sprint 106
LIKED: |  | LACKED:
LEARNED: |  | LONGED FOR:
Sprint 106
LIKED: |  | LACKED:
LEARNED: |  | LONGED FOR:
Sprint 106
LIKED: |  | LACKED:
LEARNED: |  | LONGED FOR:
Sprint 106
LIKED: |  | LACKED:
LEARNED: |  | LONGED FOR:
Sprint 106
LIKED: |  | LACKED:
LEARNED: |  | LONGED FOR:
Focus Time - promotes deep work, autonomy, satisfaction and reduces stress
Or perhaps a bi-weekly no meeting day?? AKA GSD-Day https://www.atlassian.com/team-playbook/plays/gsd-day